## New Feature
需求来源 | 需求描述 | 优先级 | 需求分析 |  | 功能设计 |  |  |  | 备注 |  | 技术评估 |  |  | 资源评估
|  |  | 场景描述 | 需求拆分 | 功能细化 | 设计PIC | 输出文档 | 输出计划 |  | 研发PIC | 技术方案 | 架构设计 | 代码方案 | 工作量 | 可用人力
RTV Oost | Ability to export audio file via common gateway | Mandatory | MHB素材导出给第三方的常规流程。 | [HNPT-272] Ability to export audio file via Common Gateway - Select video+audio clip or audio clip in ML and Web CM, export it as audio only file - Audio file will be exported via Common Gateway - Audio format will be configured by MPC policy, WAV and MP3 will be supported | 1- MPC新增CommonGW导出策略 1) 导出格式为WAV 2) 默认最大为8轨音频 3) 支持N制和P制 4) 支持导出到share folder和ftp 2- CS ML支持导出WAV纯音频文件到第三方 1) 支持将音视频素材或纯音频素材导出为WAV纯音频文件 2) 支持指定音频轨道 3) 导出源音频轨道不足8轨时自动补静音 4) 支持导出到ftp和share folder 3- WEB CM支持导出WAV纯音频文件到第三方 1) 支持将音视频素材或纯音频素材导出为WAV纯音频文件 2) 导出源不足8轨时自动补静音 | 曾祥平 |  |  |  | 聂家刚 |  | ML MPC CM CMAPI |  | 0
| Editor FRs (Refer to Hive Editor RTV Oost issue list) | TBD
Comcast | Live Logging Tool | Mandatory | 同MBH V1.0 特别说明一下[HNPT-273]的场景: In typical scenario, the operator would decide how long he need for the logging marker before the mark point when he decide to make the marker. And normally a certain duration after the mark point is also needed to make sure he could get a complete highlight. | 继承MBH V1.0, 新增: [HNPT-273] Logging: Ablity to specify the duration of action after press action button. Provide different duration options for logging marker before and after the mark points - The duration before and after the point which operator make marker should be applied to the logging maker - Operator would like to select the duration before make marker by some quick operation, E.g. provide buttons to select 30s, 20s, 10s - After the operator make maker, the post duration should be applied according to a setting (based on a duration or a percentage configuration) [HNPT-274] Support to export logging marker of clip as XML or TXT - Operator would like to export logging marker as xml or txt from logging terminal [HNPT-240] 支持logging tool，以及多镜头打点 * Ability to link several clips in a logging session * Sync clips with timecode if available or use the usual options (start, end or marker) * Apply the same logging marker to all clips simultaneously when marker is saved * Ability to choose which clip is used for preview during the logging session Additional requirements to go further and propose a trulls unique feature: * Provide a Multicam preview to see each clips simultaneously during logging session * Ability to give a title to each clip and add the title in the marker's metadata for each clip (helps easily finding the right marker when searching: "goal" marker of "Clip 2" for example) * When logging in Multicam mode, ability to click on a camera angle first to add the clip title as "Source" metadata in the marker. This helps saying: this marker has been added because of an event seen in camera angle 2 --> easier search for users) [HNPT-280] Support dual screen mode for Live Logging [SRC] 播放器时间线(CT, SV, Browser)上可以通过tooltip方式显示action/member/title | 基础功能： 1-LiveLogging要继承Sonaps LiveLogging的所有功能。 | 陈骁昂 |  |  |  | 郝勇 | 解决遗留问题 变采编播长度更新 抽帧逻辑变动 |  |  | 5
[5 empty] | 2-支持自定义action的持续时间 1）触发action那一刻之前的持续时间以及之后的持续时间，都需要支持自定义 2）用户可以在界面上快速指定触发action的前后持续时间，比如 30s, 20s, 10s | 陈骁昂 |  |  |  | 郝勇 |  |  |  | 2
[5 empty] | 3-支持将logging marker导出为XML或者TXT | 陈骁昂 |  |  |  | 郝勇 | 业务场景不明确，设计讨论中 |  |  | ？
[5 empty] | 4-多镜头打点 1）支持同时加载多个素材到Logging player 2）对多个素材进行同步播放，停止与打点，以素材时码为基准同步。 3）产生Logging maker时，同步应用到当前Logging player加载的所有素材。 4）当有多个素材加载到Logging player时，支持选择任意一个已加载的素材作为播放器的参考画面 | 陈骁昂 |  |  |  | 郝勇 | 1.不同时播放多个素材 2.只对采集完成的素材 |  |  | 3
[5 empty] | 5. 支持双屏显示 交互功能： | 陈骁昂 |  |  |  | 郝勇 | 识别双屏和单屏并作相应的界面调整 |  |  | 2
[5 empty] | 6. CT 上需要在鼠标移动到 marker点的时候，显示marker点的元数据信息。 | 陈骁昂 |  |  |  | 聂家刚 | 设计讨论中 |  |  | ？
[5 empty] | 6. SV 上需要在鼠标移动到 marker点的时候，显示marker点的元数据信息。 7. NOVA支持在ML的Logging Maker的搜索结果中，将maker拖拽到时间线 8. NOVA支持在ML的Logging Maker的搜索结果中，将maker拖拽到SV | 陈骁昂 |  |  |  | 郑程丹 | "1.SV和Mark List显示Logging Marker，显示SV现有支持的元数据，不支持Action等Logging Marker的其他特有元数据。 2. 支持拖拽ML窗口的Mark点上线，上SV，用OLE拖拽协议。" |  |  | 7
[5 empty] | 9. WEB CM也需要支持根据logging marker的action, memeber, title进行搜索 | 陈骁昂 |  |  |  | 张兴亮 | 设计讨论中 |  |  | CM: 1
[5 empty] | 10. JOVE也需要支持根据logging marker的action, memeber, title进行搜索 11. JOVE支持搜索Logging Marker 12. JOVE支持把Logging Maker的搜索结果上SV或者时间 | 陈骁昂 |  |  |  | 郑程丹
| Flexible playout control that’ allows to back to previous /next story by button | Mandatory |  | [HNPT-260] Allow to back to previous/ next story to CUE/PLAY Always keep the original order for channel assignment even change story order |  | 王娟 |  |  |  | 王磊 | NAB定制逻辑
| Sports News broadcasting operation that’s allow to preview then Play as VTR panel which allows different POW window to show | Mandatory |  | [HNPT-265] Sports News broadcasting operation that’s allow to preview then Play as VTR panel which allows different POW window to show. Support playout while ingesting by using a virtual VTR control panel |  | 王娟 |  |  |  | 王磊 | 时效性是技术方案考虑的重点
| Fast to Air -register recording clip to POW, Playlist and From Web CM with In/out points | Mandatory |  | [HNPT-261] Support register recording clip to playout channel (POW) or playlist directly, from Web CM with In/out points |  | 王娟 |  |  |  | 聂家刚 | 采集后送播 不分段 |  |  | CMAPI:1 CM:1 PL: ML:
| Consolidation with SM/Logging Marker by Trim | Mandatory |  | [HNPT-279] Ability to create new clip by scene marker/ logging marker by consolidation: - Load clip in Clip Trimmer - Select target scene marker and logging marker - Save as new clip by consolidation | 1- CT支持将marker点生成一个新素材 1) 包括scence marker和logging marker 2) marker点可选择 2- web browser上支持将marker点生成一个新素材 1) 包括scence marker和logging marker 2) marker点可选择 | 段鑫 |  |  |  | 聂家刚 | scene marker已有初级功能 logging mark需求待确认 应用场景还没有说清楚，还要继续讨论 |  |  | ？
| Web CM supports to preview recording clip and metadata creating(EM/SM etc) | Mandatory |  | [HNPT-262] Ability to browse recording clip on Web CM and Web Editor Make and save markers during preview | 1. 正在采集的素材支持在WEB CM 上进行预览 2. 正在采集的素材支持在WEB CM 上编辑元数据信息、打mark点并进行保存 | 段鑫 |  |  |  | 黄大剑 | JOVE支持边采边编素材。 1.采集中素材用DASH方式（SDK) 2.SV通过H5检测素材长度 3.SV播放，定时刷新素材长度（能否做到平滑？） 4.上时间线时，检测素材长度 5.时间线上素材Trim时，检测素材长度。 详细技术方案待讨论 |  |  | ?
| SNS distribution with tag | Medium |  | [HNPT-264] The ability to add tag for the clips before publishing them to social media. | 1- SNS发布介绍Comments编辑框中，支持,添加Tag | 林偌黠
| Eliminate audio channel in web Quick Editor | Mandatory |  | [HNPT-281] In current version video and audio channels are combined. Operators want to eliminate audio channels without impact video channels. | 1- 支持选择素材音频通道上线 | 林偌黠 |  |  | 还需要技术预研，但一定要在1.3实现 | 贺益谦 | 素材进SV，时间线VA轨时，可选择音频轨道，两轨一组，需详细设计。
| Register Event from Web Editor | Mandatory |  | [HNPT-282] - Ability to register ingesting event from Web Editor to playlist - The ingested content after assignment need to be sychronized in Web Editor - Ability to set in/out point before register to event. - Ability to register the whole clip to playout. In this case the ingested content after assigmment need to be sychronized to playout server as well. | 1- 支持注册到Event 1) 注册方法及规则参照Hive Editor | 林偌黠 |  |  |  | 肖杨 | 注册控件修改，仿PREM使用的CM控件 CMAPI支持合成到播出接口 JOVE调用控件接口 JOVE增加菜单或按钮，弹出OA窗口选择Event发送播出。JOVE触发并传递参数给OA窗口页面，流程由系统处理。 | JOVE MPC PL CMAPI |  | JOVE：？ CMAPI：1 CM: 2
| Ability to show latest clips (Today, This Week, My clips etc) | Mandatory |  | [HNPT-268] Support "Today", "This week", "My Clip" folder in Material list and Web CM to show the latest clip or favorite clip. - All the clips created within today/this week/ by the operator himself should be displayed in this folder - This could be a shortcut instead of real folder. The clips could be in different folders but linked from their original path to this folder. | 1- WEB CM/CS ML中新增三个特殊文件夹显示特定素材 1) 新增"Today"文件夹显示当天Hive产生的新素材 2) 新增"This week"文件夹显示本周Hive产生的新素材 3) 新增"My Clip"文件夹显示登录者创建的素材 4) 三个特殊文件夹均有特定的图标 5) 特殊文件夹下的素材支持的操作与普通文件夹下的基本一致，但不能作为粘贴的目标文件夹 6) 特殊文件夹下的素材只是源素材的一个逻辑Link，源素材删除，则特殊文件夹下的素材相应删除 7) 特殊文件夹下的素材会随着源素材的更新而自动更新 | 段鑫 |  |  |  | 聂家刚 | 功能雏形已有，按照高级搜索方式做 | CM JOVE PREM/AE ML CMAPI |  | 如果不考虑自动刷新 CMAPI:0.5 ML:1 CM:1
TV2 Lorry | Near-line archive: Support NAS/HDD as archive media | Mandatory |  | 见MBH V1.2 设计文档 [HNPT-110] Support NAS / HDD storage as archive medium [HNPT-19] Archive any type of asset | 1- 支持归档到NAS / HDD 1) NAS/HDD与ODA为同一级，即只支持T1→T2或T1→T2两极结构的归档，不支持T1→T2→T3三级结构 2) 支持更多元数据级别的自动归档策略配置 3) 归档到NAS/HDD的规则及流程与归档到ODA一致 4) 支持归档后根据策略配置自动删除在线高质量 5) 支持离线素材标识及属性页"Archived"标志 (归档到HDD和ODA有不同的标识) 6) 支持归档后继承CC/LTC/VITC 7) 支持离线素材的过滤及搜索 2- 支持从NAS/HDD回迁 1) 与ODA回迁规则及流程一致 2) 支持整段回迁及打点回迁 3) 支持回迁继承CC/LTC/VITC 4) 支持片段回迁到源素材 | 曾祥平 |  |  |  | 王熙 | 需要和Hive确认是否能（或如何）区分NAS / HDD 需要和设计讨论终端呈现方式 | CM ML CMAPI HIVE |  | CM: 1 ML：1 CMAPI: 0.5 HIVE:?
| Support to auto retrieve | Mandatory |  | [HNPT-112] Auto retrieve when sending to air | 1- 下列流程支持自动回迁(NAS/HDD/ODA) 1) JOVE合成 2) CT注册到播出 3) web browser注册到播出 4) 导出到CommonGW第三方 | 曾祥平 |  |  |  | 聂家刚 | 技术方案待讨论 ZCD: JOVE发送合成时，系统流程需自行通过时间线使用的素材信息去处理回迁流程。 | CM ML CMAPI HIVE |  | ？
| Support ENPS trigger archive | Mandatory | 支持从ENPS发起归档 | 与Sonaps相同功能. [HNPT-334] Support ENPS trigger archive as we did in Sonaps | 1- 支持ENPS归档 1) ENPS里面可以设置archive flag，触发归档流程 2) ENPS里面对应的script可以归档到archive | 曾祥平 |  |  |  | 王富贵 |  |  |  | MOS: 0.5 CMAPI: 0.5 HIVE:?
| Nearline Archive: migration | Mandatory | 对于TV2Lorry而言是老设备和老素材继续利用; 对于将来的项目而言, 会有更多HSM的需求出现 | [HNPT-333] Provide migration tool for customer upgrade from Sonaps to Hive | 1- 支持sonaps系统升级 1)保留sonaps的archive元数据 | 曾祥平 |  |  |  | 聂家刚 | 技术方案待讨论 |  |  | ？
| Near-line Archive: Support archive and retrieve sequence | Mandatory | 节目信息归档， 类似于素材归档。 | 1：Sequence类似Material可以归档回迁 2：Sequence相关的素材随Sequence归档，都走整段(片段)归档，且不重复归档。 3：Sequence回迁，先关素材自动回迁， 都走整段(片段)回迁。 [HNPT-109] Ability to send Hive Editor editing sequences to Hive archive. * Sending the sequence file * Sending all the media used in the sequence (video as well as non video, graphics ...) * Offer the ability to consolidate the media (send used portions with handles) to archive Ability to retrieve a Hive Editor sequence from Hive archive: * Retrieve the sequence asset * Retrieve each element linked to the sequence | 1- 支持节目归档(NAS/HDD/ODA) 1) 节目的编辑信息 2) 节目相关的素材（包括音视频及图片文本等非音视频素材）(考虑NRCS产生的script??) 3) 若素材只有部分被节目使用，则只有被使用的部分自动归档 2- 支持节目回迁(NAS/HDD/ODA) 1) 节目的编辑信息 2) 节目相关的素材（包括音视频及图片文本等非音视频素材） | 曾祥平 |  |  |  | 聂家刚 | 需要大剑明确方案 |  |  | ？
| Support ActiveX integration with ENPS for Hive Proxy Edito | Mandatory | 要求与XPRI NS一样的ActiveX方式实现与ENPS集成 | [HNPT-299] 同XPRI NS设计: - ENPS中双击素材, load到SV; 如果proxy editor尚未启动, 弹出login窗口, 登录后load素材到SV; - ENPS中双击planning, load planning相关的采集素材中的最后一个素材到SV, 同时load所有素材名到SV的素材列表; | 1- ENPS中双击素材 1) load到SV; 2) 如果proxy editor尚未启动, 弹出login窗口, 登录后load素材到SV; 2- ENPS中双击planning, 1) load planning相关的采集素材中的最后一个素材到SV 2) load所有素材名到SV的素材列表; | 王娟 |  |  |  | 郑程丹 | 使用sonyccc库(32bit)新建MOS消息接收服务进程(32bit)，服务进程和非编进程(64bit)通讯发送解析后的MOS消息 | NOVA CMAPI ML |  | NOVA:5 CMAPI：0.5 ML：0.5
Les Echo | Support AE Graphic in Web Editor | Mandatory | 在Web Editor上，AE Graphic入库Hive后preview并在Web Editor上使用. | [HNPT-298] 1. Display Adobe AE templates inside Hive web editor - Adobe templates is first rendered by Adobe and imported to Hive. - The AE graphics will be displayed in a defined folder in Hive Content Management folder tree as any other media. 2. Modify text in Web Editor titling tool - Texts can be directly added and edited (font, size, color, position, etc.) in Preview window by using the Titling tool provided by Web editor. - Timeline sequences with defined video and graphics layers (for AE graphics, text, logo, etc.) can be defined per group of users 3. Preview AE templates - The AE graphics imported to Hive can be previewed by web editor or Web Content Management 4. Render timeline sequence (video + audio + graphics) |  | 林偌黠 |  |  |  | 黄大剑 | 需要大剑明确方案 ZCD: 1.如果与Automatic IT集成，需弹出AIT的字幕模板编辑页面，编辑页面返回字幕素材。 2.字幕素材的存放形式，GIF(低质）+ MXF（高质），JOVE和Editor需支持这种素材。 | JOVE CMAPI HIVE
N24 | Support Octopus for NRCS integration | Mandatory | 支持与其他NRCS相同流程 | [HNPT-310] Support Octopus as NRCS option - By MOS - Support same workflow as we did for ENPS/iNews/Open Media | 1- 支持Octopus集成 1) 集成方式及流程与ENPS类似 2) sonaps捷克项目已支持Octopus集成，功能的测试是PSE根据QA提供的用例完成的。由PDT联系获取测试报告提供给研发 | 曾祥平 |  |  |  | 王富贵 |  | MOS ML |  | MOS:4
NAB Demo | Auto-packaging: Template based packaging for faster Internet/Mobile workflow | High | 同NAB场景 | [HNPT-331] 同NAB方案, 要求可用性改进: - Template可配和选 - 不选择Template时可以单独调整参数 | 1- 以Demo功能方式支持与NAB的Auto package功能 2- 改进模板配置 | 段鑫 |  |  |  | 郑程丹 | 沿用NAB方案建议纳入 需要JOVE实现模板创建 ZCD: 1.在NAB已有方案上，JOVE支持模板编辑。 2.需加入LUNA合成 3.MPC走LUNA合成还是NOVA合成，需确定选择方案 | JOVE
Original V1.3 | Web editor improvement (Audio, SNS, event distribution) | High |  | [HNPT-199] * Ability to select tracks from source clip used in timeline * Ability to manage timeline mapping to audio output * Provide split audio editing * Keyframe audio level adjustment * Support audio meter [HNPT-332] SNS/event distribution from Web Editor | 见Internal Improvement | 林偌黠
| Support more internet browser | Middle |  | [HNPT-90] Potential browsers to support: * Apple Safari * Microsoft Edge * Mozilla Firefox * Microsoft Internet Explorer
| Maintenance features | Mandatory |  | [HNPT-222] * Ability to export the whole system config as an xls or xml (or something else) file * Ability to select which part / module of the system's configuration to export as an xls or xml (or something else) file * Ability to restore the whole system's configuration from a previsously exported file * Ability to restore selected parts / modules of the system's configuration from a previsouly exported file. | 1- 支持网管参数的导入导出 1) 文件格式不限 2) 支持所有参数的导入导出 3) 支持部分参数的导入导出 | 陈骁昂 |  |  |  | 肖杨 王熙 | 格式定义 |  |  | 网管：4 HIVE:6 | hive暂无人力
| Support 3rd party archive workflow by Common Gateway | High |  | [HNPT-117] * "Archive to 3rd party" menu in CM * Export to hot folder with XML metadata * Add archive status in CM * Keep proxy online for some configurable retention time * Relink with original asset if the file is retrieved from 3rd party archive (with proper metadata info) | 1- 支持归档到第三方 1) 在CS ML和CM中支持归档高质量完整的素材到第三方 2) 采用CommonGW归档到第三方 3) 支持导出XML元数据 4) 增加归档到第三方的状态3rd Party Archive Status 5) 一个素材只能归档一次 2- 支持第三方回迁 1) 第三方回迁时要继承素材GUID 2) 第三方回迁时元数据和物理文件需要更新 3- 支持已归档到第三方的素材自动删除 1) 自动删除高质量 2) 自动删除低质量和元数据 | 曾祥平 |  |  |  | 聂家刚
| Support ProRes and DNxHD | High |  | [HNPT-200] * Ability to import ProRes via Import list in C/S ML and Web CM * Ability to import ProRes via Common Gateway without transcoding * Ability to import ProRes via Common Gateway with transcoding * Ability to create proxy files for ProRes * Ability to preserve alpha channel in ProRes and keep it in proxy * Ability to export ProRes via Common Gateway without transcoding * Ability to transcode to ProRes when exporting via Common Gateway [HNPT-203] * Support ProRes files in the timeline * Support mixed editing with multiple formats on the timeline including ProRes * Ability to manage alpha channel in ProRes * Ability to render timeline to ProRes format [HNPT-201] * Ability to import DNx via Import list in C/S ML and Web CM * Ability to import DNx via Common Gateway without transcoding * Ability to import DNx via Common Gateway with transcoding * Ability to create proxy files for DNx * Ability to preserve alpha channel in DNx and keep it in proxy * Ability to export DNx via Common Gateway without transcoding * Ability to transcode to DNx when exporting via Common Gateway [HNPT-202] * Support DNx files in the timeline * Support mixed editing with multiple formats on the timeline including DNx * Ability to render timeline to DNx format | 1- 支持ProRes格式 2- 支持DNxHD格式 | 曾祥平
| Change aspect ratio in Web Editor (Portrait, Zoom, move) | Mandatory | No direct link to any business but this is a must have feature that many customers are requesting and that competition is already providing (VizRT with Viz Story). | [HNPT-194] * Provide a crop mask for square aspect ratio * Provide a crop mask for portrait aspect ratio (aka 9:16) * Ability to track masks with keyframes easily (drag and drop style) * Ability to define both masks with tracking separately in web editor (ex the sequence has a square mask, and a portrait mask each of them with its own tracking --> see Viz Story as a good example) * Ability to select which mask to apply when publishing to a destination * Provide standard 4:3 / 16:9 aspect ratio conversion effect like available in XPRI | 见Internal Improvement | 林偌黠
| Auto packaging for export | High |  | [HNPT-195] * Ability to select items to add to a clip when exporting it via Common Gateway of publishing it to Social Networks (company logo, heading clip, trailing clip ...) * Ability to select each item independently so user can customize the output * Ability to create export / publishing policies containing the different packaging items so that users don't have to do it on their own each time the publish something) * Ability to import several templates (log and trailing / heading clips) ce,truly into the system * Ability to select the clip / template to use for each publication among the imported ones. |  | 段鑫
| Genealogy Metadata: Multiple generations backward/forward | Mandatory | 用于素材版权追踪和使用处理 | 见MBH 1.0-1.2 设计 [HNPT-22] Introducing the "One generation forward / backward" metadata back: Support to check and find parents and children of the clip Support indicate the used portion as well as necessary metadata Support easy access right control according to copy right Genealogy Metadata need to be accessible through API | 1- 支持one generation backward，即一个素材的源 1) 右键菜单打开，用Source Material List列表显示素材的源 2) Source Material List中支持双击打开源素材 3) 源素材被删除，one generation关系还存在 4) 包括如下操作： CS ML: Copy, trim, Local Render, MPC Render, ML→OA, ML→Playlist, CT→Event, Retrieve CM: Copy, trim, CM→Playlist, browser→Event, Retrieve JOVE: Save New Clip Premiere: Render and Export Import List: Import from XDCAM 2- 支持one generation forward，即一个素材的目标 1) 右键菜单打开，用Target Material List列表显示素材的目标 2) Target Material List中支持双击打开目标素材 3) 目标被删除，one generation关系存在 4) 包含的操作与one generation forward一致。即关系是双向的 3- 提供API接口获取Genealogy数据 | 曾祥平 |  |  |  | 聂家刚 | 需要确认业务应用场景，再根据应用场景来设计技术方案 | CM ML CMAPI HIVE |  | CM：？ ML：？ CMAPI：？ HIVE：4 | Hive（肖雄）
| Material ID workflow | High |  | 见MBH 1.0-1.2 设计 [HNPT-21] Introducing Material ID metadata back to the system and the workflows associated: Support unique material ID in the system with customized rule Material ID can be managed as metadata and can be the file name when clip is exported. User could assign clip to playlist by inputting material ID Provide a configurable Material ID generation mechanism as well as the ability to receive it from a 3rd party system
| Maintenance Feature – Screenshot collection | Mandatory | Maintenance guy want to get running status from windows VMs and physical servers and get screenshots from factory or any support center instead of checking them on customer site. This is a request from PS team. | [HNPT-167] Ability to monitor and get screenshot from windows VMs and physical servers remotely in Zeddis Monitoring Webpage. |  | 陈骁昂 |  |  | window的已经支持了，hive节点不需要
| Support more I/O board options: BMD on PMS | Medium |  | [HNPT-89] 替代X001作为PMS同步卡 |  | 王娟
| Support more I/O board options: SAMS/ Field editor | Mandatory |  | [HNPT-88] 作为SAMS的可选I/O卡 RedLink作为SAMS候选, 优先级Mandatory. |  | 王娟 |  |  |  | 杨乐 |  |  |  | 24
|  |  |  | [HNPT-88] 作为Field Editor的可选I/O卡 Field Editor优先级Middle |  | 王娟 |  |  |  | 郑程丹 |  |  |  | 20
| Support erasure code for storage fault tolerant mode | Low |  | MBH无功能设计. 作为存储的新增可选模式, 完成性能测试和与应用的兼容性测试 [HNPT-43]
| Customized Metadata – Phase 3: User rights on metadata tabs | Mandatory | V1.2未完成部分 | [HNPT-127] User rights on metadata tabs * Ability to define access rights on each metadata tab separately * Ability to define modification rights on each metadata tab separately * Ability to define access or modification rights to metadata tab separately for a user group * Ability to define access or modification rights to metadata tab separately for individual users | 1- 基于元数据tab页的用户权限管理 1) tab页访问权限 2) tab页修改权限 3) 基于用户组的tab页权限(注意一个用户可以属于多个用户组的case) 4) 基于用户的tab页权限 | 曾祥平 |  |  |  | 肖杨 |  |  |  | 网管：3
| Improved user space management – Phase 2 | High | V1.2未完成部分 | [HNPT-176] Ability to disable space quota Ability to set soft or hard quota Space ownership concept |  | 陈骁昂 |  |  |  | 聂家刚
| Cost down-VM上面跑的服务尽可能合并到一个VM中 |  |  | [HNPT-278] Combine current VM into one VM like Ingest server as example to reduce the system cost. | [5 empty] | 聂家刚
| Customized Metadata – Phase 3: Search for cutomized metadata in advanced search | Mandatory | V1.2未完成部分 | [HNPT- 173] Search for customized metadata in advanced search * Ability to add all the created customized metadata fields to the advanced search window * Ability to search the customized metadata field from the advanced search tool. | 1- 自定义元数据的高级搜索 1) 高级搜索的搜索项设置中支持选择自定义元数据项 2) 能设置的搜索项为用户能访问的元数据项 3) 支持根据自定义元数据项进行搜索 | 曾祥平 |  |  |  | 聂家刚 | CM控件变化大 技术方案待讨论 |  |  | ML:2 CMAPI:1 CM:4
| Customized Metadata – Phase 3: Display cutomize metadata in Material List's list view | Manatory | V1.2未完成部分 | [HNPT-61] Display customize metadata in Material List's list view * Ability to add any customized metadata field to the list view in Material List * Ability to remove any customized metadata field from the list view in Material List * Save the material list list view config for each user so it is carried across all GUIs (user doesn't need to update the view any time he starts a GUI including web CM). | 1- 自定义元数据的列表显示 1) List Mode中能设置列表项为自定义元数据 2) 能设置的显示项为用户能访问的元数据项 3) List Mode中能显示自定义元数据项 | 曾祥平 |  |  |  | 聂家刚 | 需求待确认 实现方案待确认
| Customized Metadata – Phase 3: Mandatory metadata | Mandatory | V1.2未完成部分 | [HNPT-125] Mandatory metadata Full requirements to be discussed. Some basic requiremenst are: * Make metadata field mandatory * Prevent the import from happening if metadata field is missing * Define a default value in Common Gateway if field missing | 1- Madatory必填项之前与David讨论后不考虑标准版实现，以后项目需要再考虑 | 曾祥平 |  |  |  | 聂家刚
| Support Windows Server 2016 | Mandatory | It appears 2012 is now superseded by 2016, and there are issue with purchasing Server 2012. | [HNPT-276] Support Windows Server 2016 for the services which are still running in Windows Server VM. |  | 曾祥平 |  |  |  | 杨军 | 建议不做。 windows server 2012 Extended Support 2023年1月10日。 windows server 2012 R2 Extended Support 2023年1月10日。
Note on C34: Xiangping.Zeng: PDT将优先级从High修改为Mandatory
Note on C37: Xiangping.Zeng:

## Internal Improvement
功能 | 功能设计
| 功能细化 | 设计PIC | 研发PIC
Field Editor改进 | 1- 支持拖拽方式实现local节目上传 2- Field Editor支持过程中登陆 3- 改进Field Editor本地库参数的配置 | 曾祥平 | 聂家刚
Playout 支持播出结束后自动发起归档 | 1- 对event设置归档标识 2- event播出结束后自动归档event相关的素材 3- event相关的script文稿信息自动归档 | 曾祥平 | 王磊
WEB CM改进 | 1- 支持分页功能，解决单个文件夹中文件数量过多，加载慢以及操作困难的问题。 | 段鑫 | 张兴亮
| 2- list模式改进，现有list模式操作不便 ，图标过大，应考虑其它显示方式.以便用户操作 | 段鑫
| 3- MARK检索结果界面改进 | 段鑫
| 4- 用户退出时自动记录当前操作的文件夹，再次登陆时自动定位到上次最后一次使用的目录 | 段鑫
| 5- Upload支持黑名单方式，禁止一些特定文件类型引入至WEB CM | 段鑫
| 6- 支持拖拽方式上载文件夹上载 1) 保留文件夹结构 2) 显示上载进度 | 段鑫
| 7- 支持用户操作权限的控制 1) 所有支持的权限及规则参照CSML | 段鑫
| 8- 批量上载改进 1) 不能同时进行，先五个完成了后再继续其它的 2) 若某个上载任务出错，则继续上载其他任务 3) 考虑增加任务监控 | 段鑫
SNS发布 | 1- 支持CM与JOVE上发起发布到SNS | 林偌黠 | 张兴亮
| 2- 新增发布类型Instagram 1) Video + Comments | 林偌黠
| 3- 支持发布界面结果预览 | 林偌黠
| 4- 支持选择幅面16:9/9:16/1:1 1) CM与JOVE方式不同, 2) CM上选择为固定 3) JOVE可在时间线上调整 | 林偌黠
Autopackage | 1- 添加片头片尾 2- 选择发布质量 3- 选择发布首帧 4- 加水印 | 段鑫 | 郑程丹
审查 | 1- 发布结果预览
| 2- 再次编辑 | 林偌黠
JOVE | 1. 音频Keyframe | 林偌黠 | 贺益谦
| 2- 特技调节 1) Cross Fade 支持调节 2) 优化其他特技调节方式 | 林偌黠
| 3- 自由选择素材音频通道 | 林偌黠
| 4- 合成素材16:9/9:16加强 1) 使用Keyframe | 林偌黠
| 5- 视音频轨道分离 1) 考虑与Imovie方法相似 | 林偌黠
| 6- VO改进 1) 操作方式改进 2) VO去噪 | 林偌黠
| 7- 时间线自动保存 | 林偌黠
| 8- Timeline Panel改进 1) Text轨道收起或变窄 | 林偌黠
| 9- 图片特技 | 林偌黠
| 10- 合成结果发布到SNS | 林偌黠
| 11- 合成结果注册到OA | 林偌黠
AE Plugin | 1- 易用性改进 | 林偌黠 | 王富贵 | 细节？
| 2- Leo Echo工程进入HIVE | 林偌黠 |  | 不懂，认不到
Premiere Plugin | 1- Subclip支持 | 林偌黠 | 王富贵 | 需要预研
| 2- 支持Https协议 | 林偌黠
| 3- Offline模式 | 林偌黠 |  | 不清楚
Hive | 当一个素材内容权限为private时，应该只有admin角色和creator可以查看并修改此素材 | 林偌黠 | 王熙

## Pended Bug
Module | ID | Headline | Design PIC
CM | GEN200015104 | CM属性页和播放器均没有显示change marker | 段鑫
| GEN200015027 | jove或premiere render的素材modify on显示为空
| GEN200014962 | 预览文件夹时，在metadata的basic info里used space永远...
| GEN200014836 | [CM]树形结构特殊字符排序不准确
| GEN200014832 | [CM]help点击没反应
| GEN200014511 | [CM]filelist上不显示物理文件完整路径也不能复制路径
| GEN200014510 | [CM]SNSPublish下的素材可以编辑元数据
| GEN200013827 | [CM]文件夹名较长或文件夹深度较深时，树形结构没有自动产生滚动条
| GEN200013763 | [CM]列表模式不能通过鼠标框选文件
| GEN200013559 | 【cm】在oa folder下素材右键后无exist in playout ...
| GEN200013533 | [CM]文档产生的pdf文件在p盘uX根目录下
| GEN200013505 | [CM]选中素材后切换显示模式，下拉菜单没滚动到对应的位置
| GEN200013483 | [CM]创建OA Material文件夹，提示信息不准确
| GEN200013472 | [CM]CM引入素材，素材名带有后缀名
NOVA RENDER TO ML的素材在 WEB CM 上不能进行播放
SNS发布 | GEN200014711 | bmp发布到twitter失败 | 林偌黠
| GEN200014710 | tag发布到facebook失败
| GEN200014708 | tga,tif,tiff发布到twitter上不显示图片
AE Plugin | GEN200013056 | HD/SD排序不正确 | 林偌黠
Premiere Plugin | GEN200013938 | 更新补丁QA9.3.3后，Premiere上登录CM失败，在QA9.2.3版本上Premiere登录CM是正确的 | 林偌黠
| GEN200013388 | mac上Premiere和ae的cm插件在素材名字过长时无气泡显示
Archive | GEN200014993 | 带CC的素材离线后打点回迁素材高质量在cutlistdemo里没有CC | 曾祥平

## 评估说明
评估的目的： 明确开发过程中的不确定因素，并制定对应的具体措施，从而从时间、方案和资源上做出可保障的计划并实现
技术评估 | 技术方案 | 明确大的技术实现方案， 避免方向性错误。比如V1.2通过信任域实现多域用户认证。比如实现YouTube发布的技术方案 | 不一定每个功能点都需要确认技术方案
| 架构设计 | 在技术方案确认后，明确模块之间的结构和逻辑，以及接口关系。比如和HIVE、CMAPI等之间的逻辑接口等
| 代码方案 | 具体的实现方案， 是重构还是增量，要兼容旧版本，具体的工作分工等
资源评估 | 工作量 | 基于技术评估的大体工作量
| 可用人力 | 930之前可投入V1.3的实际人力资源