## Bug
解决情况 | CQ ID | Key | Summary | Status | Resolution
SP2 | snp4100062912 | EUSPSCTV-32 | <mosobj> sent by SONAPS after <mosReqAll> do not contain <objPath> information | Closed | Fixed | 胡真瑞
SP2 | snp4100062947 |  | MOS GW stop | Closed | Fixed | 王富贵
SP2 |  | EUSPSCTV-37 | In MOS message <objDur> is in number of fields but all other timecode based metadata are in number of frames | Closed | Fixed | bugid=?
SP2 |  | EUSPSCTV-60 | Assign an OA mateiral from a different studio in Octopus is not working | Closed | Fixed | 聂家刚
SP2 | snp4100062760 | EUSPSCTV-10 | <objDur> value inconsistent in XML and MOS Message | Closed | Fixed | 聂家刚
SP3 |  | EUSPSCTV-55 | after NRCS sent mosReqObjAction = Update to an OA Place holder the Place holder cannot be used any more | Closed | Fixed | 胡真瑞
SP3 | snp4100064126 | EUSPSCTV-163 | Wrong <CreationDate> exported in XML | Closed | Fixed | 聂家刚
SP3/SP4 | snp4100064180 | EUSPSCTV-158 | PlaceHolder of the Octopus display is incorrect in OA Material folder of ML after modify title name of PlaceHolder in Octopus ML. (SP3 resolve) Octopus modify <objType>, <objGroup>, <objDur> and <description> values Sonaps responses NACK and update nothing. (SP4 resolve) | Closed | Fixed | 胡真瑞
SP4 | snp4100064258 |  | Some of the deleted files not reported to Octopus as deleted | Closed | Fixed | 聂家刚
SP4 |  | EUSPSCTV-183 | Prompter in Voice over mode has no line breaks and part of script is invisible | Closed | Fixed | ？？
SP4 |  | EUSPSCTV-141 | clip title created in Register to OA->Use MaterialID doesn't contain sequence name | Closed | Fixed | ？？
SP4 | snp4100064370 |  | MosGateway send mosListAll messag e without the objPaths node | Closed | Fixed | 胡真瑞
SP5 | snp4100064428 | EUSPSCTV-167 | Deleting a folder to transh can, SONAPS doesn't send MOS notifications for materials in the folder | Closed | Fixed | 胡真瑞
SP6 | snp4100064517 | EUSPSCTV-171 | rundown is moved to date 31.12.1899 after <roMetadataReplace> | Resolved | Fixed | 王磊
SP6 | snp4100064492 | EUSPSCTV-202 | MOS GW crash when responding to <mosReqAll> with Pause=0 or >0 | In Progress | Unresolved
SP7 | snp4100065135 | EUSPSCTV-170 | in some cases, the "Created" date of object is updated, when placeholder is populated with material | In Progress | Unresolved
The issue itself is not fixed and the symptom is the same with ENPS. The customer removed the issue from online issue list though. Closed as won't fix. |  | EUSPSCTV-118 | When an user Active X session is closed in Net Manager, Octopus session is closed in user terminal | Closed | Won't Fix | bugid=?
已解决，但是没有信息 |  | EUSPSCTV-46 | When ingesting to OA place holder, the fake duration is not sent via MOS | Closed | Fixed | bugid=?
提供WA:if main Omneon is down and backup Omneon is available, in NM, Studio Management ->Terminal Channel Setting, swap Protocol Type for each virtual PMS. if it was main, change to standby and vice versa. then restart the terminal, and open Playlist again. |  | EUSPSCTV-110 | Clips transferred from Sonaps (OA) to Backup Omneon server only are displayed incorrectly in Sonaps playlist | Closed | Won't Fix | bugid=?
| snp4100062753 | EUSPSCTV-24 | Octopus Call ClipTrimmer Plugin?? Media offline displayed on CT | Closed | Fixed | 聂家刚
|  | EUSPSCTV-33 | No accurate logs of what have been sent by MOS GW to NRCS via MOS message
|  | EUSPSCTV-67 | While SDI ingesting, the proxy is not playable by any 3rd party systems - Octopus, WMP, meidainfo (open header) | Closed | Won't Fix | bugid=?
|  | EUSPSCTV-70 | When assign an OA material to rundown, SONAPS always sent <mosObj> update with new 'change date' | Closed | Won't Fix | 胡真瑞
|  | EUSPSCTV-105 | Story Scripts are not always displayed in SONAPS | Closed | Fixed | bugid=?
|  | EUSPSCTV-168 | rundown contains large number of stories caused MOS communication to stop | Closed | Won't Fix | 胡真瑞
|  | EUSPSCTV-172 | MOS GW did not send <roAck> | Assign | Unresolved
|  | EUSPSCTV-173 | MOS GW sent heartbeat to wrong socket | Assign | Unresolved
|  | EUSPSCTV-178 | MosListAll sent by MOS GW doesn't comply with MOS Protocol 2.8.x | Closed | Fixed | bugid=?
|  | EUSPSCTV-185 | It is not possible to render to OA from Web Cutter (mobile version only) | Assign | Unresolved
|  | EUSPSCTV-188 | Prompted "Do you want to update material to event?" dialog after deploying SP4 | Closed | Fixed | 聂家刚
|  | EUSPSCTV-189 | Delete and purge OA Material, MOS updates are not correctly sent to Octopus after SP4 deployment | Closed | Fixed | bugid=?
|  | EUSPSCTV-190 | When OA material is moved to a different folder, SONAPS sends 'deleted' updates to the other studio of Octopus | Open | Unresolved | 胡真瑞
| snp4100064548 | EUSPSCTV-191 | After SP4, SONAPS sends MOS messages <mosObj> for clips in PE | Resolved | Fixed | 聂家刚
| snp4100064479 | EUSPSCTV-194 | Octopus inserted a new story, SONAPS did not execute and returned error in roAck | In Progress | Unresolved
| snp4100064524 | EUSPSCTV-199 | SONAPS acknowledged delete object command from Octopus but did not delete | Assign | Unresolved
| snp4100064512 | EUSPSCTV-227 | MOS GW didn't answer MOS message until timeout | Resolved | Fixed | 王富贵
| snp4100064799 | EUSPSCTV-229 | MOS GW sometimes doesn't send MOS item replace | In Progress | Unresolved
| snp4100064588 | EUSPSCTV-240 | MOS GW Ostrava - rundown not getting any story updates | In Progress | Unresolved
| snp4100064830 | EUSPSCTV-272 | incorrectly formatted <mosObj> message sent from Sonaps to Octopus | Resolved | Fixed | 王富贵
| snp4100065040 | EUSPSCTV-280 | MOS error messages from Sonaps | In Progress | Unresolved
| snp4100065188 | EUSPSCTV-290 | It is not possible to use placholder if the object in the story is changed in Octopus | In Progress | Unresolved
Issue was fixed by SP3 but reoccur after SP4 is deployed. and after SP4, not only the clips moved to the trash can but also the new clips in PE\bin are updated to Octopus. |  | EUSPSCTV-114 | Sonaps MOS device SERVER sends materials moved from Bin to Trash in PE as separate MOS objects to Octopus | Closed | Fixed | bugid=?
mosgw配置问题，已经解决，不用发补丁 |  | EUSPSCTV-126 | SONAPS sends large amount of MOS Messages | Closed | Fixed | 王富贵
Not sure if the patch helped. Later there were multiple issues found regarding heartbeat exchange between SONAPS and Octopus that could cause delays of MOS communications. After those issues were resolved, no new incidents reported. The solution was applied by an Octopus update, though the root cause might be with SONAPS. |  | EUSPSCTV-156 | MOS GW update Octopus with delays | Closed | Fixed | bugid=?
octopus 本身问题 |  | EUSPSCTV-111 | when user close the ActiveX plug-in from Octopus user session is not released | Closed | Fixed | 聂家刚

## New Feature
Version | Title | How to fix
SP2 | Octopus integration- Render a sequence to playout server | a) Render a sequence to playout- Sonaps to send via MOS, the render duration in <mosObj> <objDur> when render starts (currently <objDur> "0" is sent) | 哪个模块改的？
SP2 | Octopus integration- Add from ML ActiveX to Octopus Rundown PlaceHolder - material from a different studio | a) Sonaps to send in <mosItemReplace> a right combination of <mosID> & <ObjID> for the story (mosID should not be changed e.g. when a clip of Studio 2 is used in a rundown of Studio 1) | 聂家刚
SP3 | Octopus-Sonaps intergration: user logging session is not closed when Active X is closed in Octopus terminal. | Provide Sonaps interface information to Octopus side. Octopus will release patch based on the interface to fix it. | 聂家刚
SP3 | Customer require Sonaps should not send materials moved from XPRI Bin to Trash in PE as separate MOS objects to Octopus | Not send new MOS object create message to NRCS when user move clip from XPRI bin to trash can. | 聂家刚
SP3 | Octopus-Sonaps intergration: the clips are not released after click Modify and close CT window without press Save . | Provide Sonaps interface information to Octopus side. Octopus will release patch based on the interface to fix it | 聂家刚