## Summary
Purpose of this document
This document is written in order to prevent the omission in a check at the time of a patch release. When a patch is planed,
Reference
| patch_release_20101013.vsd |  |  | workflow of a patch release is defined
Contents
The following sheets should be reported at the specified stage. The yellow cell in the sheet should be filled.
0. pre-test report
|  | When | Patch test is requested or planed
|  | Report from | LiuXiang or PIC of test
|  | Report to | Kakita, Kageyama, ZhouXiaobin, WuHonglian, WuZhan and tester
1. test report (without result)
|  | When | The testcase is made
|  | Report from | LiuXiang or PIC of test
|  | Report to | Kakita, Kageyama, ZhouXiaobin, WuHonglian, WuZhan and tester
After made this report, it should be reviewed with PDT and PSS.
2. test report (with result)
|  | When | The test is finished
|  | Report from | LiuXiang or PIC of test
|  | Report to | Kakita, Kageyama, ZhouXiaobin, WuHonglian, WuZhan and tester
3. release file check
|  | When | Final release file is prepared to FTP
|  | Report from | LiuXiang or PIC of test
|  | Report to | Kakita, Kageyama, ZhouXiaobin, WuHonglian, WuZhan and tester
After 2 and 3 are prepared, we hold a QA internal meeting for patch release judgement with Kakita and Kageyama.
The result should be reported by WuZhan.
After the meeting, WuZhan will inform QA result to PDT, Kageyama will inform to ATG design.

## pre-test report
Background |  |  | Patch information & schedule |  | Scope of test
Czech TV customer request some improvements on design defect during their test and trial period, and also reported some issues including bug and SPEC issue. |  |  | Patch Name | V5.4.2 SP4 | Issue modification & side effect
|  |  | Base Version | V5.4.2 SP3
|  |  | Release To | Czech TV
|  |  | Test System | QA 100 system
|  |  | PIC | Liuxiang
|  |  | Tester | zhuji;wangxiuya;gaoshijie;leidongmei
|  |  | Testing by CD QA | 2016/10/14~2016/10/26
|  |  | Case review by ATG QA | No need
|  |  | Doc check by CD&ATG QA | 2016-10-26
|  |  | Buffer | None
|  |  | Release (committed with SC) | 2016-10-27
8 SPEC improvement issues | [5 empty] | Can be reproduced in V5.4.2SP3? | Merge from? | spec change or not?
Function ID(PSE ID) | Subsystem | Reporter | Description
AP11-C27 AP13-C25 AP12-C24 | ML | PSE | Display of actively used IP address for machines equipped with dual network adapter |  |  | Yes |  | Yes
AP14-C41 AP16-C35 AP15-C35 | ML | PSE | Add setting to control enable/disable |  |  | Yes |  | Yes
AP14-C49 AP16-C40 | ML | PSE | AD Import Tool |  |  | Yes |  | Yes
AP14-C53 AP16-C42 | ML | PSE | Clip named "(1)" in OA folder |  |  | Yes |  | Yes
\ | Playout | PSE | 3 seconds playout support |  |  | Yes |  | Yes
AP11-B17 AP13-B16 AP12-B16 | ML | PSE | In case CT is opened first than no remote nodes are displayed in ML afterwards |  |  | Yes |  | Yes
AP11-B17 AP13-B16 AP12-B16 | ML | PSE | ClipTrimmer ActiveX plugin is not initialized properly under some circumstances and because of this it is not able to play video and display any metadata. |  |  | Yes |  | Yes
AP11-C35 AP13-C30 AP12-C29 | ML | PSE | Prohibit avi importing by ML |  |  | Yes |  | Yes
9 bug fixing
Bug ID | CHLOE ID | Module | Description |  | Why QA missed
snp4100063912 | EUSPSCTV-128 | Ingest | Wrong timestamp in VTR ingest workflow |  | All Sonaps verison has this issue before, QA missed to check this kind of VTR task by FOW, because QA did not use this task start time | Yes
snp4100064258 | \ | MOS | Some of the deleted files not reported to Octopus as deleted |  | It related to Octopus integration | Yes
snp4100064259 | EUSPSCTV-150 | Ingest | Deletion of certain folders from Isilon after not being used |  | Spec change | Yes |  | Yes
snp4100063909 | EUSPSCTV-79 | GTM | "Wrong display in GTM Transfer tasks in GTM are always shown as done by pr-so-tx-srv-01(transfer server1) which is not true. |  | Spec change | Yes |  | Yes
snp4100064255 | EUSPSCTV-49 | Ingest | VTR control slow |  | It's not bug. Same issue as snp4100063330 in SP2 (SPEC improvement to drop the redundancy check logic for LTC) | Yes
snp4100064180 | EUSPSCTV-158 | MOS | Placeholder corruption |  | It related to Octopus integration | Yes
snp4100064365 | \ | Ingest | cannot import from XDS |  | The influence scope from developer showed XDCAM Upload but not xdcam Import | Yes
snp4100064369 | \ | Editor | Prompter issue in Voice Over mode |  | QA is confirming because we had not confirmed we missed this issue by which verison | Yes
snp4100064370 | \ | MOS | objpaths missing in MOS message |  | It related to Octopus integration | Yes
Necessity of the stability test of XPRI NS |  |  | Unnecessary
(Please describe the reason, if unnecessary) No modifacation is related to stability
Necessity of the Performance test |  |  | Unnecessary
No modifacation is related to Performance
SPEC change with fixing issues |  |  | Yes there is SPEC change
(Please describe the status of PSS confiramtion to S/C and ATG, if there is SPEC change) All the SPEC change was requested from PSE.
Note on B16: 作者: Marked as red means not reproduced
Note on B26: 作者: Marked as red means not reproduced

## Ingest Report
No.1
Issue ID |  | snp4100063912
Subsystem |  | Ingest
Description |  | VTR upload task's create time is always the last taks's create time
Cause |  | N/A
Why QA missed |  | Test case omitted in base version
QA missed Test type |  | function
Instant Action |  | N/A |  |  | `
Reproducible (yes/no) |  | yes
Frequency |  | always
How to Fix |  | Modify the start time to current time when the task start
Influence Range |  | Create task on FOW
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | The create time of ingest tasks | 1.VTR upload task create time is current system time 2.Ordinary taks start by FOW,the create time is current system time | 1.VTR upload task 2.Create tasks by FOW[Manual task;schedule task create by FOW;Split clips on FOW]
1-1 |  |  |  | 1.VTR upload environment 2.VTR upload task create by FOW | 1.Switch current channel to VTR Signal 2.Check the Specify VTR TC and filing in the markin and markout point 3.Click Start Recording button 4.Check the create time of the task on FOW,ML when ingesting 5.Check the create time of the task on FOW,ML when ingested | 4.Then create time is current system time 5.The create time is the same as[4] | 10 | ok
1-2 |  |  |  | 1.VTR upload environment 2.VTR upload task create by FOW 3.Insert manual task between two VTR upload task | 1.Switch current channel to VTR Signal 2.Check the Specify VTR TC and filing in the markin and markout point 3.Click Start Recording button 4.Check the create time of the task on FOW,ML when ingesting 5.Check the create time of the task on FOW,ML when ingested 6.Create manual task on FOW by click Start Recording button 7.Repeat Step[1-5] | 4.Then create time is current system time 5.The create time is the same as[4] 7-1.Then create time is current system time 7-2.The create time is the same as[7-1] | 10 | ok
1-3 |  |  |  | 1.Create task by FOW[Manual task] | 1.Click the Start Recording button on FOW 2.Check the create time of the task on FOW,ML when ingesting 3.Stop task on FOW/FSW 4.Check the create time of the task on FOW,ML when ingested | 2.Then create time is current system time 4.The create time is the same as[4] | 10 | ok
1-4 |  |  |  | 1.Create task by FOW[Schedule task create by FOW] | 1.Filing in the duration on FOW 2.Click the Start Recording button on FOW 3.Check the create time of the task on FOW,ML when ingesting 4.Check the create time of the task on FOW,ML when ingested | 3.Then create time is current system time 4.The create time is the same as[4] | 10 | ok
1-5 |  |  |  | 1.Create task by FOW[Split clips on FOW] | 1.Click the Start Recording button on FOW 2.Check the create time of the task on FOW,ML when ingesting 3.Click Split Manually button on FOW 4.Check the create time of 1st task on FOW,ML when ingested 5.Check the create time of 2nd task on FOW,ML when ingesting | 2.Then create time is current system time 4.The create time is the same as[2] 5.The create time is current system time | 10 | ok
No.2
Issue ID |  | snp4100064259
Subsystem |  | Ingest
Description |  | Deletion of certain folders from Isilon after not being used
Cause |  | N/A
Why QA missed |  | Requirement change
QA missed Test type |  | function
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | always
How to Fix |  | Clear iconfiles folder
Influence Range |  | Cache clean
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Clear Cache files | 1.All the files/folders in Cache folder must be deleted(include Cache folder) | 1.Clear Cache tool:XDCAM Cache Cleaner.exe 2.Import device:[U1/U2;XDCAM;XDS;P2;EX]
1-1 |  |  |  | 1.Run XDCAM Cache Cleaner.exe 2.Import device:[U1/U2;XDCAM;XDS;P2;EX] | 1.Connect U1/U2;XDCAM;XDS;P2;EX to Sonaps System 2.Open Ingest Terminal 3.Open Import List 4.Check the Cache folder of the devices workpath in the central storage 5.Run XDCAM Cache Cleaner.exe tool 6.Check the Cache folder in the central storage | 4.The Cache folder has been generated automatically. 6.All the files/folders in Cache has cleared(include Cache folder) | 5 | ok
1-2 |  |  |  | 1.Run XDCAM Cache Cleaner.exe 2.Import device:[U1/U2;XDCAM;XDS;P2;EX] 3.Create new files/folders in Cache by manual | 1.Connect U1/U2;XDCAM;XDS;P2;EX to Sonaps System 2.Open Ingest Terminal 3.Open Import List 4.Open Cache folder of the devices workpath in the central storage and create files/folder in Cache folder(folder named:planningmetadata) 5.Run XDCAM Cache Cleaner.exe tool 6.Check the Cache folder in the central storage | 6.All the files/folders in Cache has cleared(include Cache folder) | 5 | ok
1-3 |  |  |  | 1.Case[1-1] 2.Create Cache folder by manual | 1.Run Case[1-1] 2.Open the devices workpath in the central storage and create a folder named Cache 3.Run XDCAM Cache Cleaner.exe tool 4.Check the Cache folder in the central storage | 6.Cache folder has been deleted | 5 | ok
1-4 |  |  |  | 1.Case[1-1] 2.Create new files/folders in Cache by manual | 1.Run Case[1-1] 2.Open the devices workpath in the central storage and create a folder named Cache 3.Open Cache folder and create some files/folder in Cache folder(folder named:planningmetadata) 4.Run XDCAM Cache Cleaner.exe tool 5.Check the Cache folder in the central storage | 5.All the files/folders in Cache has cleared(include Cache folder) | 5 | ok
1-5 |  |  |  | 1.Delete clips in ML and purge | 1.Connect U1/U2;XDCAM;XDS;P2;EX to Sonaps System 2.Open Ingest Terminal 3.Open Import List 4.Import a clip into ML 5.Delete the clip in ML and purge it 6.Run XDCAM Cache Cleaner.exe tool 7.Check the Cache folder in the central storage | 7-1.All the files/folders in Cache has cleared(include Cache folder) 7-2.The files in iconfiles folder will be deleted | 5 | ok
No.3
Issue ID |  | snp4100064255
Subsystem |  | Ingest
Description |  | To control the VTR to create a VTR upload task is very slowly
Cause |  | Delveloper have some historical modified programs but has not been commented out the scrap process
Why QA missed |  | Design is not specified
QA missed Test type |  | performance
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | Commented out the scrap process
Influence Range |  | To VTR upload task created by FOW
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Perfornmance | The delay time of VTR Upload task | The delay time of VTR upload task is less than 25s | 1.Nport and COM+ 2.PAL HD/SD
1-1 |  |  |  | 1.VTR upload task create by:FOW 2.Ignore the rewind time 3.Sony matrix | 1.Switch the singal to VTR 2.Filing in the Markin and Markout point on FOW 3.Press start recording button and started timing with a stopwatch 4.When the VTR rewin to find markin point stop and record the time 5.Keep on timing when the VTR status from stop&play to start record | 4.The time is close to 20s 5.The time is close to 20s (close to 20s is accepted by customer) | 5 | ok (21s)
1-2 |  |  |  | 1.VTR upload task create by:FSW 2.Ignore the rewind time 3.Sony matrix | 1.Create a VTR upload schedule task on FSW(Filing in Markin and Markout) 2.Start timing when the VTR status from the beginning to start record | 2.The time is close to 20s (close to 20s is accepted by customer) | 5 | ok(20s)
1-3 |  |  |  | 1.VTR upload task create by:BDL 2.Ignore the rewind time 3.Sony matrix | 1.Create a VTR upload task on BDL(Filing in Markin and Markout)and submit the task 2.Start timing when the VTR status from the begining to start record | 2.The time is close to 20s (close to 20s is accepted by customer) | 5 | ok(21s)
1-4 |  |  |  | 1.VTR upload task create by:Planning 2.Ignore the rewind time 3.Sony matrix | 1.Create a planning of VTR upload task on Plan List (Filing in Markin and Markout) 2.D&D the planning to FSW 3.Start timing when the VTR status from the beginning to start record | 3.The time is close to 20s (close to 20s is accepted by customer) | 5 | ok(17s)
No.4
Issue ID |  | snp4100064365
Subsystem |  | Ingest
Description |  | XDS can not refresh the materials in Import List
Cause |  | Upper program did not send root path to MPC
Why QA missed |  | The influence of developer gave is XDCAM Upload but not xdcam Import
QA missed Test type |  | function
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | Remove write fixed path from MPC in program code.
Influence Range |  | XDCAM Import
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | The FTP devices refresh materials in Import List | 1.The FTP devices can refresh materials correctly in Import List | 1.Import devices:[XDCAM PDW-HD1500;XDS-PD1000]
1-1 |  |  |  | 1.Import devices:XDCAM-HD1500 | 1.Connect the XDCAM PDW-HD1500 into Sonaps system 2.Insert a xdcam disc into PDW-HD1500 3.Start Import Service 4.Login Ingest Terminal 5.Open Import List 6.Check the PDW-HD1500 materials in Import List 7.Import the materials | 6.All the materials in the disc must be refresh in Imort List 7.Can import normally | 5 | ok
1-2 |  |  |  | 1.Import devices:XDS-PD1000-DISC | 1.Connect the XDCAM XDS-PD1000 into Sonaps system 2.Insert a xdcam disc into XDS-PD1000 3.Start Import Service 4.Login Ingest Terminal 5.Open Import List 6.Check the XDS-PD1000-DISC materials in Import List 7.Import the materials in XDS-DISC | 6.All the materials in the disc must be refresh in Imort List 7.Can import normally | 5 | ok
1-3 |  |  |  | 1.Import devices:XDS-PD1000-HDD | 1.Connect the XDCAM XDS-PD1000 into Sonaps system 2.Add some materials into XDS-PD1000 HDD storage 3.Start Import Service 4.Login Ingest Terminal 5.Open Import List 6.Check the XDS-PD1000-HDD materials in Import List 7.Import the materials XDS-HDD | 6.All the materials in the XDS-HDD must be refresh in Imort List 7.Can import normally | 5 | ok
1-4 |  |  |  | 1.Import devices:XDS-PD1000-MEMORY | 1.Connect the XDCAM XDS-PD1000 into Sonaps system 2.Insert EX Card into XDS-PD1000 3.Start Import Service 4.Login Ingest Terminal 5.Open Import List 6.Check the XDS-PD1000-MEMORY materials in Import List 7.Import the materials XDS-MEMORY | 6.All the materials in the XDS-MEMORY must be refresh in Imort List 7.Can import normally | 5 | ok
2 | Compatibility | The Local devices refesh materials in Import List | 1.The local devices can refresh materials correctly in Import List | 1.Import devices:[U1/U2;P2;EX(fat);EX(UDF);exFat]
2-1 |  |  |  | 1.Import devices:[U1/U2;P2;EX(fat);EX(UDF);exFat] | 1.Connect the devices[U1/U2;P2;EX;EX(fat);EX(UDF);exFat] to Ingest Termianl machine 2.Start local Import Service 3.Login Ingest Terminal 4.Open Import List 5.Check the devices [U1/U2;P2;EX;EX(fat);EX(UDF);exFat] materials 6.Import the materials of these devices | 6.All the materials must be refresh in Imort List 7.Can import normally | 5 | ok
AIS Install & Rollback Test
Description
Test Case | [6 empty] | Test times
Unzipped check |  | Compare unzipped AIS package with actual QA test package by compare tool to confirm files are same |  |  |  |  | 1 | OK
Install |  | after installed by AIS, compare all the patch files in each PC with patch file package of V5.4.2 SP4 |  |  |  |  | 1 | OK
Rollback |  | after Rollback by AIS, compare all the patch files in each PC with back up folder of V5.4.2 SP2 |  |  |  |  | 1 | OK
Manually Install & Rollback Test
Description
Test Case | [6 empty] | Test times
Install |  | after installed by Manually, compare all the patch files in each PC with patch file package of V5.4.2 SP4 |  |  |  |  | 1 | OK
Rollback |  | after Rollback by Manually, compare all the patch files in each PC with back up folder of V5.4.2 SP2 （also QA confirmed rollback to SP3 is OK） |  |  |  |  | 1 | OK
Release note check by CD and ATG
OK
Test Result
All case OK (except some NG case with CQ ID & explanation)
Troubles been found during testing
CQID |  | Phenomenon and reproducing steps |  |  |  |  | Severity | Current status
snp4100064380 |  | ML]注册素材到OA少于3秒的提示内容没有把5 seconds更新为3 seconds |  |  |  |  | Emergency | Confirmed
snp4100064394 |  | ML]NM中version up 的开关没有对应的描述信息f |  |  |  |  | Emergency | Confirmed
snp4100064395 |  | [ML]NM中version up 的开关0和1 效果一样，实际功能没实现 |  |  |  |  | Necessary | Confirmed
snp4100064396 |  | 非编在双网卡的情况下不能打开时间线. |  |  |  |  | Emergency | Confirmed
snp4100064399 |  | [ML]Octopus打开CT后不登录，再打开ML登录后看不到remote站点 |  |  |  |  | Urgent | Submitted
snp4100064401 |  | [Ingest]Cache Cleaner缓存清理不干净 |  |  |  |  | Emergency | NoProblem | PSS confirmed that custermor only request to delete icon file and icon file folder in Cache folder (QA also confirmed in CHLOE description), if so, current behavior is OK
snp4100064402 |  | [PL]注册素材到Event少于3秒的提示内容没有把5 seconds更新为3 seconds |  |  |  |  | Emergency | Confirmed
snp4100064403 |  | [Web]Web cutter register to event can not support version up. |  |  |  |  | Emergency | NoProblem | Because requirement from customer had not described web cutter portion, it was reported by QA’s related testing, then PSS confirmed with PSE,and PSE know it with the reason caused by web does not support to select ‘Material ID’. and ’ web does not support to select Material ID’ is SPEC even it might not be described clearly in SPEC document.But since they confirmed by VC, there is no email evidence. So I think it’s better PSS explain it in judge meeting.
snp4100064404 |  | [Web]Web cutter register to event can not fill placeholder. |  |  |  |  | Emergency | NoProblem | Because requirement from customer had not described web cutter portion, it was reported by QA’s related testing, then PSS confirmed with PSE,and PSE know it with the reason caused by web does not support to select ‘Material ID’. and ’ web does not support to select Material ID’ is SPEC even it might not be described clearly in SPEC document.But since they confirmed by VC, there is no email evidence. So I think it’s better PSS explain it in judge meeting.
snp4100064405 |  | [Web]Web注册素材到Event未支持3秒 |  |  |  |  | Emergency | Confirmed
snp4100064408 |  | [PL]ML D&D素材到Event，没有支持3秒素材 |  |  |  |  | Emergency | Confirmed
snp4100064409 |  | [PL]支持多个版本的情况下，从MV拖拽sequence到event注册成功后，event的Version没有变化 |  |  |  |  | Emergency | Confirmed
snp4100064415 |  | [PL]发起迁移任务时，迁移调度会出现not responding |  |  |  |  | Emergency | Confirmed
Stability test result
No need
SPEC change confirmation result to S/C and ATG by PSS
The SPEC change was requested from PSE.
Actual workload for this patch
PDT |  | 1
Development |  | 70
PS |  | 40
QA |  | 48
Release judge
OK
Note on B1: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on B20: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A40: 作者: CQ ID and CHLOE ID
Note on A48: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B51: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A58: 作者: CQ ID and CHLOE ID
Note on A66: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B69: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A79: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B82: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A89: 作者: CQ ID and CHLOE ID
Note on A108: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B111: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test

## XpriNS report
No.1
Issue ID |  | snp4100064369
Subsystem |  | XPRI
Description |  | Prompter issue in Voice Over mode
Cause |  | There is not a line feed when play the prompter
Why QA missed |  | The text used is not long enough .
QA missed Test type |  | WF
Instant Action |  | N/A
Reproducible (yes/no) |  | Yes
Frequency |  | Always
How to Fix |  | Line feed correct when dubbing and paly the prompter
Influence Range |  | Line feed when dubbing and paly the prompter
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Line feed of pormpter | Line feed correct when play the prompter | 1.The file with automatic line feed text 2.The file with manual line feed text . 3.The file with automatic line feed text and manual line feed. 4.Input text in prompter (automatic line feed / maunal line feed / both have automatic line feed and maunal line feed)
1-1 |  |  |  | 1.The file(test01) with automatic line feed text | 1.Login XpriNS and create a new project 2.Open the Prompter window 3.Open the meun of the Prompter window and click open and choose the file(test01),then click "OK"button" 4.Open the Audio Voice Over Tool window 5.Click "Record" button in Audio Voice Over Tool window and click "Play"button in prompter window | 2.Open the prompter window success 3.Open the test01 in prompter success,and the display of prompter display correct. 5.After click "Play"button ,the prompter display correct (line feed correct) | 5 | OK
1-2 |  |  |  | 2.The file(test02) with manual line feed text . | 1.Login XpriNS and create a new project 2.Open the Prompter window 3.Open the meun of the Prompter window and click open and choose the file(test02),then click "OK"button" 4.Open the Audio Voice Over Tool window 5.Click "Record" button in Audio Voice Over Tool window and click "Play"button in prompter window | 2.Open the prompter window success 3.Open the test02 in prompter success,and the display of prompter display correct. 5.After click "Play"button ,the prompter display correct (line feed correct) | 5 | OK
1-3 |  |  |  | 3.The file (test03) with automatic line feed text and manual line feed. | 1.Login XpriNS and create a new project 2.Open the Prompter window 3.Open the meun of the Prompter window and click open and choose the file(test03),then click "OK"button" 4.Open the Audio Voice Over Tool window 5.Click "Record" button in Audio Voice Over Tool window and click "Play"button in prompter window | 2.Open the prompter window success 3.Open the test03 in prompter success,and the display of prompter display correct. 5.After click "Play"button ,the prompter display correct (line feed correct) | 5 | OK
1-4 |  |  |  | 4.Input text in prompter (automatic line feed / maunal line feed / both have automatic line feed and maunal line feed) | 1.Login Xprins and create a new project 2.Open the Prompter window 3.Input some text in prompter with automatic line feed 4.Open the Audio Voice Over Tool window 5.Click "Record" button in Audio Voice Over Tool window and click "Play"button in prompter window | 2.Open the prompter window success 3.Can input text and display correct 5.After click "Play"button ,the prompter display correct (line feed correct) | 5 | OK
1-5 |  |  |  |  | 1.Login XpriNS and create a new project 2.Open the Prompter window 3.Input some text in prompter with maunal line feed 4.Open the Audio Voice Over Tool window 5.Click "Record" button in Audio Voice Over Tool window and click "Play"button in prompter window | 2.Open the prompter window success 3.Can input text and display correct 5.After click "Play"button ,the prompter display correct (line feed correct) | 5 | OK
1-6 |  |  |  |  | 1.Login XpriNS and create a new project 2.Open the Prompter window 3.Input some text in prompter with both have automatic line feed and maunal line feed) 4.Open the Audio Voice Over Tool window 5.Click "Record" button in Audio Voice Over Tool window and click "Play"button in prompter window | 2.Open the prompter window success 3.Can input text and display correct 5.After click "Play"button ,the prompter display correct (line feed correct) | 5 | OK
2 | Function | Line feed of pormpter | The line feed display correct in prompter from NRCS | 1.Input some text in event with (automatic line feed / maunal line feed / both have automatic line feed and maunal line feed) in NRCS.
2-1 |  |  |  | 1.Input some text in event with (automatic line feed / maunal line feed / both have automatic line feed and maunal line feed) in NRCS. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event12. 2.Synch the rundown1 to Sonaps. 3. Open event12 and input some text with automatic line feed 4.Login Sonaps XpriNS, and open Playlist window and show rundown1. 5.Open Material List then D&D a ready clip to timeline. 6.D&D sequence from MV to event1. 7.Open prompter window on timeline menu bar. 8.Open the Audio Voice Over Tool 9.Click "Record" button 10.Click "Play"button in Prompter window after click "Record"button 11.Check the display of prompter | 1.Create successfully. 2.Synch successfully. 3.Input successfully. 6. Register sequence to event 1 successfully. 7.It will be popup the "Prompter" window, and display text correctly 8.Open the Audio Voice Over Tool success 11.After click "record" and "paly"button the prompter display correct | 5 | OK
2-2 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event 2 respectively, and create blank material to event12. 2.Synch the rundown1 to Sonaps. 3. Open event12 and input some text with maunal line feed 4.Login Sonaps XpriNS, and open Playlist window and show rundown1. 5.Open Material List then D&D a ready clip to timeline. 6.D&D sequence from MV to event 2. 7.Open prompter window on timeline menu bar. 8.Open the Audio Voice Over Tool 9.Click "Record" button 10.Click "Play"button in Prompter window after click "Record"button 11.Check the display of prompter | 1.Create successfully. 2.Synch successfully. 3.Input successfully. 6. Register sequence to event 2 successfully. 7.It will be popup the "Prompter" window, and display text correctly 10.Open the Audio Voice Over Tool success 11.After click "record" and "paly"button the prompter display correct | 5 | OK
2-3 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event 3 respectively, and create blank material to event12. 2.Synch the rundown1 to Sonaps. 3. Open event12 and input some text with both have automatic line feed and maunal line feed 4.Login Sonaps XpriNS, and open Playlist window and show rundown1. 5.Open Material List then D&D a ready clip to timeline. 6.D&D sequence from MV to event 3. 7.Open prompter window on timeline menu bar. 8.Open the Audio Voice Over Tool 9.Click "Record" button 10.Click "Play"button in Prompter window after click "Record"button 11.Check the display of prompter | 1.Create successfully. 2.Synch successfully. 3.Input successfully. 6. Register sequence to event 3 successfully. 7.It will be popup the "Prompter" window, and display text correctly 10.Open the Audio Voice Over Tool success 11.After click "record" and "paly"button the prompter display correct | 5 | OK
Note on B1: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test

## ML&Web report
No.1
Issue ID |  | Function
Subsystem |  | NM
Description |  | Display of actively used IP address for machines equipped with dual network adapter
Cause
Why QA missed |  | new function
QA missed Test type |  | N/A
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | N/A
Influence Range |  | kick off function of NM
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | kick off function of NM | can correct to kick off target IP for two network card PC | terminal PC have two network card: 1.ML terminal 2.NM terminal 3.Playout terminal 4.Ingest terminal 5.live logging terminal 6.Archive terminal 7.Craft terminal 8.Proxy terminal 9.GTM terminal 10.GCW setting --Optio Setting Dialog 11.MLS Option ---Option Setting Dialog 12.NRCS(ENPS\INEWS\Octopus\Open midia) ML plug
1-1 |  |  |  | 1.ML terminal | 1.login ML terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-2 |  |  |  | 2.NM terminal | 1.login NM terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-3 |  |  |  | 3.Playout terminal | 1.login Playout terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-4 |  |  |  | 4.Ingest terminal | 1.login Ingest terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-5 |  |  |  | 5.live logging terminal | 1.login logging terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-6 |  |  |  | 6.Archive terminal | 1.login Archive terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is kick off on the target machine | 5 | OK
1-7 |  |  |  | 7.Craft terminal | 1.login Craft terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is kick off on the target machine | 5 | OK
1-8 |  |  |  | 8.Proxy terminal | 1.login Proxy terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is kick off on the target machine | 5 | OK
1-9 |  |  |  | 9.GTM terminal | 1.login GTM terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is kick off on the target machine | 5 | OK
1-10 |  |  |  | 10.GCW setting --Option Setting Dialog | 1.login GCW Option terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-11 |  |  |  | 11.MLS Option ---Option Setting Dialog | 1.login MLS Option terminal 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is off kick on the target machine | 5 | OK
1-12 |  |  |  | 12.NRCS(ENPS\INEWS\Octopus\Open midia) ML plug | 1.login 3rd-part ML plug 2. login NM ,in online status display two IP 3.select target IP to kick off | 2.1. display information is correct two in online status include: Workstation、IP Address、Type、login user、login Time、Subsystem、Port 2.2 can display two IP for dual network card PC in online status 3.1 can correct to kick off the two IP successively 3.2 Check whether the program is kick off on the target machine | 5 | OK
No.2
Issue ID |  | Function
Subsystem |  | ML
Description |  | prohibit import AVI file by right click of ML
Cause
Why QA missed |  | new function
QA missed Test type |  | N/A
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | N/A
Influence Range |  | import file
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | prohibit import AVI file to ML | prohibit import AVI file by right click of ML | Through the following terminals can be import the AVI file to Sonaps for SP4 1.ML terminal 2.Playout terminal (have ML plug window) 3.Ingest terminal (have ML plug window) 4.live logging terminal (have ML plug window) 5.Craft terminal (have ML plug window) 6.Proxy terminal (have ML plug window) 7.NRCS(ENPS\INEWS\Octopus\Open midia) (have ML plug window)
1-1 |  |  |  | 1.ML terminal | 1.login ML terminal 2.right click on the blank select import--->clip by ML window 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
1-2 |  |  |  | 2.Playout terminal (have ML plug window) | 1.login playout terminal and open ML windows 2.right click on the blank select import--->clip 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
1-3 |  |  |  | 3.Ingest terminal (have ML plug window) | 1.login ingest terminal and open ML windows 2.right click on the blank select import--->clip 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
1-4 |  |  |  | 4.live logging terminal (have ML plug window) | 1.login live logging terminal and open ML windows 2.right click on the blank select import--->clip 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
1-5 |  |  |  | 5.Craft terminal (have ML plug window) | 1.login Craft terminal and open ML windows 2.right click on the blank select import--->clip 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
1-6 |  |  |  | 6.Proxy terminal (have ML plug window) | 1.login Proxy terminal and open ML windows 2.right click on the blank select import--->clip 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
1-7 |  |  |  | 7.NRCS(ENPS\INEWS\Octopus\Open midia) (have ML plug window) | 1.login 3rd-Part terminal and open ML windows 2.right click on the blank select import--->clip 3.pop import clip windows,click Browse button, pop open window | 3.1 there is not avi option in the drop down menu 3.2 can not import avi file to sonaps for SP4 | 5 | OK
No.3
Issue ID |  | Function
Subsystem |  | NM
Description |  | Add setting to version up control enable/disable
Cause
Why QA missed |  | new function
QA missed Test type
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix
Influence Range |  | NM setting about version up and effective
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Version UP | when register material to event via XpriNS, if it has been registed real material, when register again a warning message ("Can not assign material to populated event!") will be pop up to refuse material assignment. | NM setting about The function of Versioning UP : 1:enable/0:disable
1-1 |  |  |  | 1: enable | 1. Login NM 2. setting EnableEventMulVer parameter in NM as 1 | 2. the function of version up is enable | 5 | OK
1-2 |  |  |  | 0;disable | 1. Login NM 2. setting EnableEventMulVer parameter in NM as 0 | 2. the function of version up is disable | 5 | OK
1-3 |  |  | 1: enable | From MV can D&D only one sequence to the same event of NRCS. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline. 5.Open Playlist window and show rundown1, then from MV D&D sequence to event1 of the rundow1. 6.Click OK button on Register window. 7.From MV D&D sequence to event1 again.And on Registation Window, must select "Use mateiral ID". | 5.It will be popup Register Window and Studio,Rundown, Story, Event and Material ID are disable on Register Window. 6.Filling event successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1. 7.D&D successfully and version as 2/2 on event.And create a new clip on OA foder. | 5 | OK
1-4 |  |  | 1: enable | MV can register only one sequence to the same event of NRCS. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline. 5.Open MasterViewer(MV) window,then click drop-down menu and then select "Register to Playout Server". 6.Respectively select studio, rundown, story and event as StudioA, rundown1, story1 and event1. Then click OK button on Register window. 7.Repeat steps 5 and 6.And in the steps 6, on Registation Window, must select "Use mateiral ID". | 5.It will be popup Register Window and Studio,Rundown, Story, Event are usable on Register Window. 6.Filling event successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1. 7.Register successfully and version as 2/2 on event.And create a new clip on OA foder. | 5 | OK
1-5 |  |  | 1: enable | From PE can D&D only one sequence to the same event of NRCS. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline. 5.Open Playlist window and show rundown1 then from PE1 D&D sequence to event1 of the rundow1. 6.Click OK button on Register window. 7.From PE1 D&D sequence to event1 again.And on Registation Window, must select "Use mateiral ID". | 5.It will be popup Register Window and Studio,Rundown, Story, Event and Material ID are disable on Register Window. 6.Filling event successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1. 7.D&D successfully and version as 2/2 on event.And create a new clip on OA foder. | 5 | OK
1-6 |  |  | 1: enable | Right click on the sequence from PE,and can register only one sequence to the same event of NRCS | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 2.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 3.Open Material List then D&D a ready clip to timeline. 4.Right click on the sequence from PE1,and then select "Register to Playout Server". 5.Respectively select studio, rundown, story and event as StudioA, rundown1, story1 and event1. Then click OK button on Register window. 6.Repeat steps 4 and 5.And in the steps 5, must select "Use mateiral ID"on Registation Window,. | 5.Filling event successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1. 6.After click "OK" on Select Event window,it will bge popup a warning window: Can not assign material to populated event! 7.Register successfully and version as 2/2 on event.And create a new clip on OA foder. | 5 | OK
1-7 |  |  | 1: enable when register material to event via ML, if it has been registed real material, when register again a warning message ("Can not assign material to populated event!") will be pop up to refuse material assignment. | From CT can register only one clip to the same event of the NRCS. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Choose a ready material then right click and then click "Clip Trimmer" in ML. 4.Setting Mark-in and Mark-out on Clip Trimmer window, and then click "Register to Playout Server" button. 5.Respectively select studio, rundown, story and event as StudioA, rundown1, story1 and event1 on Register window. 6.Click OK button on Register window. 7.Repeat steps 3,4 and 5. 8.Click OK button on warning window. 9.Choose "Select flolder" and then click "Folder selection" on Register window. 10.Choose correcsponding studio from OA Material node then click "OK" button on "Select Folder" window. | 1.Create successfully. 2.Synch successfully. 3.Open a material successfully via CT. 4.It will be popup Register Window and Studio,Rundown, Story, Event are usable on Register Window. 5.Select successfully. 6.Register event1 successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1. 7.After click "OK" on Select Event window,it will be popup a warning window: Can not assign material to populated event! 8.It will be close warning window. 9.It will be popup "Select Folder" window. 10.Register material to studio sucessfully. | 5 | OK
1-8 |  |  | 1: enable when register material to event via ML, if it has been registed real material, when register again a warning message ("Can not assign material to populated event!") will be pop up to refuse material assignment. | From ML can D&D only one material to the same event of NRCS. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps Material Manager Terminal then open Playlist window and show rundown1, and then D&D a real material to event1 of the rundow1 from ML. 4.D&D material to event1 again. | 1.Create successfully. 2.Synch successfully. 3.Filling event1 successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1. 4.D&D successfully and version as 2/2 on event.And create a new clip on OA foder. | 5 | OK
1-9 |  |  | 1: enable when register material to event via ML, if it has been registed real material, when register again a warning message ("Can not assign material to populated event!") will be pop up to refuse material assignment. | D&D material from OA folder to event. | 1.Login NRCS client and create a rundown, story and event1,event2 to StudioA that named rundown1,story1,event1,event2 respectively, and create blank material to event1,event2. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps Material Manager Terminal then open Playlist window and show rundown1, and then D&D a real material from ML to event1 and event2 of the rundow1. 4.D&D material of event1 from OA folder of studioA to event2. | 3.Filling event1 and event2 successfully, and Version as 1/1, Material ID, Stamp, Event Title, Duration、Material Title, Total Duration（Main/Backup), SOM and EOM are right of the event1 and event2. 4.D&D successfully and version as 2/2 on event.And this material ID the same as event1. | 5 | OK
Note on B60: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test

## MPC&PL Report
No.1
Issue ID |  | AP14-C53 AP16-C42 TBA
Subsystem |  | ML
Description |  | Clip named "(1)" in OA folder
Cause |  | Spec change
Why QA missed |  | Spec change
QA missed Test type |  | Function
Instant Action
Reproducible (yes/no) |  | YES
Frequency |  | Always
How to Fix |  | Naming rules need to add the name of sequence or original clip.
Influence Range |  | A material and sequence register to Playout then display clip name.
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Clip named in OA folder | The clip of the QA name naming rules is with the original material via CT register. | "Use material ID" on Registration Window from Clip Trimmer .
1-1 |  |  |  |  | 1.Login Material Manager Terminal 2. In Public Material node, double-click a material name is HD50. 3. On "Clip Trimmer" window, click "Register to Playout Server". 4. On "Registration Window", select "Studio" as StudioA and Date as today(2016/10/13) and choice "Use Material ID" 5. Click "OK" button. 6.Check that clip name under the OA Material\StudioA\2016\10\13 folder. | 6. That clip name naming rules is with the original material which is HD50. | 5 | ok
1-2 |  |  |  |  | 1.Login Material Manager Terminal 2. In Public Material node, double-click a material name is HD50. 3. On "Clip Trimmer" window, click "Register to Playout Server". 4. On "Registration Window", select "Studio" as StudioA and Date as today(2016/10/13) and choice "Use Material ID" 5. Click "OK" button. 6.Check that clip name under the OA Material\StudioA\2016\10\13 folder. 7.Repeat step 4, 5 and 6. | 6. That clip name naming rules is with the original material which is HD50. 7. That clip name naming rules is with the original material which is HD50. | 5 | ok
2 | Function | Clip named in OA folder | The clip of the QA name naming rules is with the original material via MV. | "Use material ID" on Registration Window from MV .
2-1 |  |  |  | D&D from MV | 1.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 2.Open Material List then D&D a ready clip to timeline. 3. D&D the sequence from MV to OA Material\StudioA\2016\10\13 folder. 4. Click "OK" button. 5.Check that clip name under the OA Material\StudioA\2016\10\13 folder. | 5.That clip name naming rules is with the original material which is sequence. | 5 | ok
2-2 |  |  |  | D&D from MV | 1.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 2.Open Material List then D&D a ready clip to timeline. 3. D&D the sequence from MV to OA Material\StudioA\2016\10\13 folder. 4. Click "OK" button. 5.Check that clip name under the OA Material\StudioA\2016\10\13 folder. 6. Repeat step 3, 4 and 5. | 5.That clip name naming rules is with the original material which is sequence. 6.That clip name naming rules is with the original material which is sequence. | 5 | ok
2-3 |  |  |  | Right click on the sequence from PE | 1.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 2.Open Material List then D&D a ready clip to timeline. 3.Right click on the sequence from PE1,and then select "Register to Playout Server". 4. On "Registration Window", select "Studio" as StudioA and Date as today(2016/10/13) and choice "Use Material ID" 5. Click "OK" button. 6.Check that clip name under the OA Material\StudioA\2016\10\13 folder. | 6.That clip name naming rules is with the original material which is sequence. | 5 | ok
2-4 |  |  |  | Right click on the sequence from PE | 1.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 2.Open Material List then D&D a ready clip to timeline. 3.Right click on the sequence from PE1,and then select "Register to Playout Server". 4. On "Registration Window", select "Studio" as StudioA and Date as today(2016/10/13) and choice "Use Material ID" 5. Click "OK" button. 6.Check that clip name under the OA Material\StudioA\2016\10\13 folder. 7. Repeat step 3, 4, 5 and 6. | 6.That clip name naming rules is with the original material which is sequence. 7.That clip name naming rules is with the original material which is sequence. | 5 | ok
3 | Function | A material and sequence register to Playout. | A material and sequence register to Playout that name is right.
3-1 |  |  |  | Register a material to Playout. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4. In Public Material node, double-click a material name is HD50. 5. On "Clip Trimmer" window, click "Register to Playout Server". 6. On "Registration Window", select "Studio" as StudioA, Rundown as rundow1, Story as story1, Event as event1. 7. Click "OK" button on Register window 8. Check that clip name under the OA Material\StudioA\2016\10\13\rundow1 folder. | 8. That clip name is right which is event1. | 5 | ok
3-2 |  |  |  | D&D a material to Playout | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4. Open playlist window and show rundown1. 5.D&D a material to event1 of the rundown1. 6. Check that mateiral name under the OA Material\StudioA\2016\10\13\rundow1 folder. | 6. That material name is right which is event1. 6-2. If it is D&D again, the clip name the same as source material name in OA folder. | 5 | ok
3-3 |  |  |  | D&D a sequence to Playout. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline. 5.Open Playlist window and show rundown1, then D&D sequence from MV to event1 of the rundow1. 6.Click OK button on Register window. 7. Check that clip name under the OA Material\StudioA\2016\10\13\rundow1 folder. | 7. That clip name is right which is event1. | 5 | ok
3-4 |  |  |  | Register a sequence to Playout. | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline. 5.Right click sequence from PE then select "Register to Playout Server". 6. On "Registration Window", select "Studio" as StudioA, Rundown as rundow1, Story as story1, Event as event1. 6.Click OK button on Register window. 7. Check that clip name under the OA Material\StudioA\2016\10\13\rundow1 folder. | 7. That clip name is right which is event1. | 5 | ok
No.2
Issue ID |  | N/A
Subsystem |  | Playout
Description |  | 3 seconds playout support (original is 5 seconds limitation)
Cause |  | Spec change
Why QA missed |  | Spec change
QA missed Test type |  | Function
Instant Action
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | Changed from original 5 seconds to 3 seconds.
Influence Range |  | None
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | At least 3 seconds playout support. | A material is 3 seconds playout support. | Register a material with 3 seconds to OA Folder from ML.
1-1 |  |  |  | D&D from ML | 1.Login Material Manager Terminal. 2.D&D a material with 3 seconds from Public Material to the OA Material\StudioA\2016\10\13 folder. | 2.D&D successfully. | 5 | ok
1-2 |  |  |  | D&D from OA Folder | 1.Login Material Manager Terminal. 2.D&D a material with 3 seconds from OA Folder to the OA Material\StudioA\2016\10\13 folder. | 2.D&D successfully. | 5 | ok
1-3 |  |  |  | From CT register | 1.Login Material Manager Terminal 2. In Public Material node, double-click a material. 3. On "Clip Trimmer" window, setting duration is 3 seconds, and then click "Register to Playout Server". 4. On "Registration Window", click "Select Folder", 5.Select OA Material\StudioA\2016\10\13 node then click "OK" on Select Folder window. | 5.Register that clip successfully. | 5 | ok
2 | Function | At least 3 seconds playout support. | If the registered to playout length less than 3 seconds will be popup a warning message. | Register a material with 00:00:02:24 to OA Folder from ML.
2-1 |  |  |  | D&D from ML | 1.Login Material Manager Terminal. 2.D&D a material with 00:00:02:24 from Public Material to the OA Material\StudioA\2016\10\13 folder. | 2.D&D successfully. | 5 | ok
2-2 |  |  |  | From CT register | 1.Login Material Manager Terminal 2. In Public Material node, double-click a material. 3. On "Clip Trimmer" window, setting duration is 00:00:02:24, and then click "Register to Playout Server". 4. On "Registration Window", click "Select Folder", 5.Select OA Material\StudioA\2016\10\13 node then click "OK" on Select Folder window. | 5.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
3 | Function | At least 3 seconds playout support. | A material is 3 seconds playout support. | Register a material with 3 seconds to event from ML.
3-1 |  |  |  | D&D from ML | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4. Open playlist window and show rundown1. 5.D&D a material with 3 seconds to event1 of the rundown1. | 5. D&D and transfer to playout successfully. And duration is 00:00:3:00 on event. | 5 | ok
3-2 |  |  |  | From CT register | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4. In Public Material node, double-click a material. 5. On "Clip Trimmer" window, setting duration is 00:00:03:00, and then click "Register to Playout Server". 6. On "Registration Window", select Studio as StudioA, Rundown as rundow1, Story as story1 and Event as event1, and then click "OK" button. | 6. Register that clip and transfer to playout successfully. And duration is 00:00:3:00 on event. | 5 | ok
4 | Function | At least 3 seconds playout support. | If the registered to playout length less than 3 seconds will be popup a warning message. | Register a material with 00:00:02:24 to event from ML.
4-1 |  |  |  | D&D from ML | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4. Open playlist window and show rundown1. 5.D&D a material with 00:00:02:24 to event1 of the rundown1. | 5. Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
4-2 |  |  |  | From CT register | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4. In Public Material node, double-click a material. 5. On "Clip Trimmer" window, setting duration is 00:00:02:24, and then click "Register to Playout Server". 6. On "Registration Window", select Studio as StudioA, Rundown as rundow1, Story as story1 and Event as event1, and then click "OK" button. | 6.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
5 | Function | At least 3 seconds playout support. | A material is 3 seconds playout support. | Register a material with 3 seconds to event from Web.
5-1 |  |  |  | Web Cutter | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List. 4.Choose a ready material with H.264 then right click and then click "Web Cutter". 5.Setting Mark-in and Mark-out is 3 seconds then clik "Story Board" on Cutter window. 6.Click "Register Event" on Cutter window. 7.On Select Event window, select "Studio" as StudioA, "Date" as current date and "Rundown" as rundown1. 8.Choose the event1 then click "OK" button on Select Event window. | 6.Register that clip and transfer to playout successfully. And duration is 00:00:3:00 on event. | 5 | ok
5-2 |  |  |  | D&D to event from Web ML | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List and Playlist and show rundown1. 4.D&D a material with 3 seconds to event of the rundown1. | 4.D&D and transfer to playout successfully. And duration is 00:00:3:00 on event. | 5 | ok
5-3 |  |  |  | Register to event from material right- click menu | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List. 4.Select a 3 seconds material and right click and then select "Register to Event". 5.On Select Event window, select Studio as StudioA, Date as 2016-10-13(e.g), Rundown as rundown1 and event as event1, and click "OK" button. | 6.Register that clip and transfer to playout successfully. And duration is 00:00:3:00 on event. | 5 | ok
5-4 |  |  |  | Register Material | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List and Playlist and show rundown1. 4.On event1 right click and then select "Register Material". 5.On Upload window, click "Select" and select that you want upload material with 3 seconds. And click "OK" botton. | 5.Register that clip and transfer to playout successfully. And duration is 00:00:3:00 on event. | 5 | ok
6 | Function | At least 3 seconds playout support. | If the registered to playout length less than 3 seconds will be popup a warning message. | Register a material with 00:00:02:24 to event from Web.
6-1 |  |  |  | Web Cutter | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List. 4.Choose a ready material with H.264 then right click and then click "Web Cutter". 5.Setting Mark-in and Mark-out is 00:00:02:24 then clik "Story Board" on Cutter window. 6.Click "Register Event" on Cutter window. 7.On Select Event window, select "Studio" as StudioA, "Date" as current date and "Rundown" as rundown1. 8.Choose the event1 then click "OK" button on Select Event window. | 8.Cant not register, it will be popup a warning message: The storyboard'sduration less than 3 seconds, cannot register to the event! | 5 | ok
6-2 |  |  |  | D&D to event from Web ML | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List and Playlist and show rundown1. 4.D&D a material with 00:00:02:24 to event of the rundown1. | 4.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
6-3 |  |  |  | Register to event from material right- click menu | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List. 4.Select a material with 00:00:02:24 and right click and then select "Register to Event". 5.On Select Event window, select Studio as StudioA, Date as 2016-10-13(e.g), Rundown as rundown1 and event as event1, and click "OK" button. | 5.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
6-4 |  |  |  | Register Material | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.User with rights of studioA login WebSpace then open Material List and Playlist and show rundown1. 4.On event1 right click and then select "Register Material". 5.On Upload window, click "Select" and select that you want upload material with 00:00:02:24. And click "OK" botton. | 5.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
7 | Function | At least 3 seconds playout support. | A material is 3 seconds playout support. | Register a sequence with 3 seconds to event from XpriNS.
7-1 |  |  |  | Right click sequence from PE | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 3 seconds. 5.Right click sequence from PE then select "Register to Playout Server". 6. On "Registration Window", select "Studio" as StudioA, Rundown as rundow1, Story as story1 and Event as event1. 7.Click OK button on Register window. | 7.Register sequence and transfer to playout successfully.And duration is 00:00:3:00 on event. | 5 | ok
7-2 |  |  |  | D&D from MV | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 3 seconds. 5.Open Playlist and show rundown1. 6.D&D sequence from MV to event1. | 6.Register sequence and transfer to playout successfully.And duration is 00:00:3:00 on event. | 5 | ok
8 | Function | At least 3 seconds playout support. | If the registered to playout length less than 3 seconds will be popup a warning message. | Register a sequence with 00:00:02:24 to event from XpriNS.
8-1 |  |  |  | Right click sequence from PE | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 00:00:02:24. 5.Right click sequence from PE then select "Register to Playout Server". 6. On "Registration Window", select "Studio" as StudioA, Rundown as rundow1, Story as story1 and Event as event1. 7.Click OK button on Register window. | 7. Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | Ok
8-2 |  |  |  | D&D from MV | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 00:00:02:24. 5.Open Playlist and show rundown1. 6.D&D sequence from MV to event1. | 6.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
9 | Function | At least 3 seconds playout support. | A material is 3 seconds playout support. | Register a sequence with 3 seconds to OA Folder from XpriNS.
9-1 |  |  |  | Right click sequence from PE | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 3 seconds. 5.Right click sequence from PE then select "Register to Playout Server". 6. On "Registration Window", click "Select Folder", 7.Select OA Material\StudioA\2016\10\13 node then click "OK" on Select Folder window. | 7.Register that sequence successfully. | 5 | ok
9-2 |  |  |  | D&D from MV | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 3 seconds. 5.D&D the sequence from MV to the OA Material\StudioA\2016\10\13 folder. 6.Click OK button on Register window. | 6.Register the sequence successfully. | 5 | ok
9-3 |  |  |  | D&D a sequence to placehoder from MV | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 3 seconds. 5.D&D the sequence from MV to placeholder of the event1. 6.Click OK button on Register window. | 6.Register sequence and transfer to playout successfully.And duration is 00:00:3:00 on event. | 5 | ok
10 | Function | At least 3 seconds playout support. | If the registered to playout length less than 3 seconds will be popup a warning message. | Register a sequence with 00:00:02:24 to OA Folder from XpriNS.
10-1 |  |  |  | Right click sequence from PE | 1.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 2.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 00:00:02:24. 3.Right click sequence from PE then select "Register to Playout Server". 4. On "Registration Window", click "Select Folder", 5.Select OA Material\StudioA\2016\10\13 node then click "OK" on Select Folder window. | 5.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
10-2 |  |  |  | D&D from MV | 1.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 2.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 00:00:02:24. 3.D&D the sequence from MV to the OA Material\StudioA\2016\10\13 folder. 4.Click OK button on Register window. | 4.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
10-3 |  |  |  | D&D a sequence to placehoder from MV | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Sonaps XpriNS and create new project that named PE1 in Project Explorer. 4.Open Material List then D&D a ready clip to timeline and then setting Mark-in and Mark-out is 00:00:02:24. 5.D&D the sequence from MV to placeholder of the event1. 6.Click OK button on Register window. | 6.Cant not register, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
11 | Function | At least 3 seconds playout support. | 1.A material is 3 seconds playout support. 2.If the registered to playout length less than 3 seconds will be popup a warning message. | 1.Ingesting material …\Sony\Sonaps\Ingest Console\PHTask.ini, the ForbiddenTime =3
11-1 |  |  |  | D&D a placeholder to FOW | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Ingester Terminal and open FOW. 4.Open Material List and then D&D the placehoder of the event1 to FOW. 5.Start recording on FOW. 6.Stop recording on FOW immediately. | 6-1.If the material duartion is greater than 3 seconds, it well be stop successfully, and the clip transfer to playout successfully, and duration is greater than 3 seconds on event. 6-2.If the material duration less than 3 seconds, Cant not stop, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
11-2 |  |  |  | D&D a ingesting material to placehoder | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1 respectively, and create blank material to event1. 2.Synch the rundown1 to Sonaps. 3.Login Ingester Terminal and open FOW. 4.Start recording on FOW. 5.D&D that ingesting material to placehoder of the event1 immediately. | 5-1.If the material duration is greater than 3 seconds, it well be stop successfully, and the clip transfer to playout successfully, and duration is greater than 3 seconds on event. 5-2.If the material duration less than 3 seconds, Cant not stop, it will be popup a warning message: Please make suer the material's duration is greater than 3 cesonds! | 5 | ok
12 | Function | At least 3 seconds playout support. | On-air the event with 3 seconds is right | On-air
12-1 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2 ... event10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material with 3 seconds to all the event. 5.When material transfer to playout finished, on-air that rundown1. | 5-1On-air each event is right, and don't lost frames, don't black frames, don't blurred frames. 5-2.The playout logic is right. | 5 | ok
12-2 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2 ... event10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material with 3 seconds to all the event. 5.When material transfer to playout finished, on-air that rundown1. 6.Recue the playing event on POW. | 5-1On-air each event is right, and don't lost frames, don't black frames, don't blurred frames. 5-2.The playout logic is right. 6.Can be recue that event. | 5 | ok
12-3 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2 ... event10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material with 3 seconds to all the event. 5.When material transfer to playout finished, on-air that rundown1. 6.Pause the playing event on POW. | 5-1On-air each event is right, and don't lost frames, don't black frames, don't blurred frames. 5-2.The playout logic is right. 6.Can be pause that event. | 5 | ok
12-4 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2 ... event10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material with 3 seconds to all the event. 5.When material transfer to playout finished, on-air that rundown1. 6.Take the playing event on POW. | 5-1On-air each event is right, and don't lost frames, don't black frames, don't blurred frames. 5-2.The playout logic is right. 6.Can be take that event. | 5 | ok
12-5 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2 ... event10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material with 3 seconds to all the event. 5.When material transfer to playout finished, on-air that rundown1. 6.Stop the playing event on POW. | 5-1On-air each event is right, and don't lost frames, don't black frames, don't blurred frames. 5-2.The playout logic is right. 6.Can be stop that event. | 5 | ok
12-6 |  |  |  |  | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2, event3 respectively, and create blank material to event1 and . 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material to event1 and event3. 5.When material transfer to playout finished, on-air that rundown1. 6.When a event playing, D&D a real OA clip to event2 from NRCS. | 5-1On-air each event is right, and don't lost frames, don't black frames, don't blurred frames. 5-2.The playout logic is right. 6.D&D successfully, and cue event2 is right. | 5 | ok
No.3
Issue ID |  | AP11-B17 AP13-B16 AP12-B16
Subsystem |  | ML
Description |  | In case CT is opened first than no remote nodes are displayed in ML afterwards
Cause |  | If open CT in Octups firstly, it will login as CT mode, then get the ML site infromation (since this case, it's not login by any user account, it can olny access local site.), then use account login ML again in Octopus, system finds it already login, no need to initialize again, then this issue happen.
Why QA missed |  | SPEC change
QA missed Test type
Instant Action
Reproducible (yes/no) |  | Yes
Frequency |  | Always
How to Fix |  | Change the code order to create property page to make sure even open CT firstly then login ML can display remote site.
Influence Range |  | Octopus use the Sonaps plugin.
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | display the remote site. | Can display the remote site. | 1.There is set remote site. 2.That login user have the rights of the see remote site.
1-1 |  |  |  | 1.Open CT first then open ML plugin. | 1.Login Octopus client and then open "Media" on the right side of the menu. 2.Select a material from Media and right click->Plugin->"CT". 3.Input the LoginName and password. 4.Select a material from Media and right click->Plugin->"ML". 5.Check the remote node in ML plugin whether display right. | 2. It will be popup the User Login window. 3.Open that material successfully and can be preview. 4.Open that ML plugin successfully. 5.It is display right. | 5 | ok
1-2 |  |  |  | Only open the ML plugin | 1.Login Octopus client and then open "Media" on the right side of the menu. 2.Select a material from Media and right click->Plugin->"ML". 3.Input the LoginName and password. 4.Check the remote site in ML plugin whether display right. | 2. It will be popup the User Login window. 3.Open that ML plugin successfully. 4.It is can display remote site and right. | 5 | ok
1-3 |  |  |  | 1.Open CT first but it does not login then open ML plugin. | 1.Login Octopus client and then open "Media" on the right side of the menu. 2.Select a material from Media and right click->Plugin->"CT". 3.It does not login, click "cancel". 4.Select a material from Media and right click->Plugin->"ML". 5.Input the LoginName and password. 6.Check the remote site in ML plugin whether display right. | 4. It will be popup the User Login window. 5.Open that ML plugin successfully. 6.It is display right. | 5 | NG snp4100064399
No.4
Issue ID |  | AP11-B17 AP13-B16 AP12-B16
Subsystem |  | ML
Description |  | ClipTrimmer ActiveX plugin is not initialized properly under some circumstances and because of this it is not able to play video and display any metadata.
Cause |  | This is compatibility problems.
Why QA missed |  | SPEC change
QA missed Test type |  | Function
Instant Action |  | Add to testing
Reproducible (yes/no) |  | YES
Frequency |  | Always
How to Fix |  | Change the code order to create property page to make sure even open CT in ML firstly then open CT can preview clip
Influence Range |  | Octopus use the Sonaps plugin.
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Preview mateial in CT | Can be preview material in CT.
1-1 |  |  |  | 1.Open ML first and close then open CT plugin. | 1.Login Octopus client and open "Media" on the right side of the menu. 2.Select a material from Media and right click->Plugin->"ML". 3.Preview a material in ML plugin. 4.Close the ML plugin. 5.Select a material from Media and right click->Plugin->"CT". 6.Input the LoginName and password. 7.Preview the material in CT. | 2.Open ML plugin seccessfully. 3.Can be preview that material. 6. Open CT seccessfully. 7.Can be preview the material in CT. | 5 | ok
1-2 |  |  |  | 1.Only preview material in CT. | 1.Login Octopus client and open "Media" on the right side of the menu. 2.Select a material from Media and right click->Plugin->"CT". 3.Input the LoginName and password. 4.Preview the material in CT. | 3. Open CT seccessfully. 4.Can be preview the material in CT. | 5 | ok
1-3 |  |  |  | 1.Open ML first and don't login then open CT plugin. | 1.Login Octopus client and then open "Media" on the right side of the menu. 2.Select a material from Media and right click->Plugin->"ML". 3.It does not login, click "cancel". 4.Select a material from Media and right click->Plugin->"CT". 5.Input the LoginName and password. 6.Preview the material in CT. | 5.Open CT seccessfully. 6.Can be preview the material in CT. | 5 | ok
No.5
Issue ID |  | snp4100064258
Subsystem |  | ML
Description |  | After deleted the folder with material from Sonaps ML, Octopus still display these material in the that folder.
Cause |  | When delete a folder with material from ML , it did not notify that material of the folder to MOSGW.
Why QA missed |  | There is not Octopus in QA.
QA missed Test type |  | Function
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | When delete a folder with material from ML , it will notify that material of the folder to MOSGW.
Influence Range |  | Sonaps sync material to NRCS.
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Delete material | If deleted material from ML, Octopus the same auto deleted that. | NRCS=Octopus
1-1 |  |  |  | Delete folder with material in ML. | 1.Login Material Manager Terminal. 2.Create a folder naming "Folder1", copy&paste 10 material in it and naming material1, material2… material10. 3.Delete the Folder1. 4.Login Octopus client. 5. Open "Media" on the right side of the menu. 6.Input material in Fulltext search textbox and click "Enter" on keyboard. 7.Select one of them and right click, and then select "Preview". 8.Check "ObjGroup" whether is Trash Can. | 7. Can search that 10 material and right. 8. ObjGroup is Trash Can. | 5 | ok
1-2 |  |  |  | Delete folder with material in OA folder. | 1.Login Octopus client and create a rundown, story and event to StudioA that named rundown1,story1, story2...story10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal and then register material to all the event. 4.Delete that rundow1 folder in OA folder. 5. Open "Media" on the right side of the menu from Octopus. 6.Input story in Fulltext search textbox and click "Enter" on keyboard. 7.Select one of them and right click, and then select "Preview". 8.Check "ObjGroup" whether is Trash Can. | 7. Can search that 10 clip and right. 8. ObjGroup is Trash Can. | 5 | ok
1-3 |  |  |  | Delete folder with Placehoder in OA folder. | 1.Login Octopus client and create a rundown, story and event to StudioA that named rundown1,storyA1, storyA2...storyA10 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Delete that rundow1 folder in OA folder. 5. Open "Media" on the right side of the menu from Octopus. 6.Input story in Fulltext search textbox and click "Enter" on keyboard. 7.Select one of them and right click, and then select "Preview". 8.Check "ObjGroup" whether is Trash Can. | 7. Can search that 10 placehoder and right. 8. ObjGroup is Trash Can. | 5 | ok
2 | Function | Sonaps sync material to NRCS. | Sonaps sync material to NRCS seccessfully and right. | NRCS=Octopus
2-1 |  |  |  | Sync new mateiral of OA folder to NRCS | 1.Login Material Manage Terminal, D&D 50 material to OA folder of StudioA. 2.Login Octopus client . 3. Open "Media" on the right side of the menu from Octopus. 4.Click F4 on keyboard in input box(there is a prompt), then select StudioA on "select option" 5.Input that material name in Fulltext search textbox and click "Enter" on keyboard. 6.Chec the search results whether right. | 6.The search results is right. It display those 50 material. | 2 | ok
2-2 |  |  |  | Sync modify mateiral of OA foder to NRCS | 1.Login Material Manage Terminal, D&D 50 material to OA folder of StudioA. 2.Login Octopus client . 3. Open "Media" on the right side of the menu from Octopus. 4.Click F4 on keyboard in input box(there is a prompt), then select StudioA on "select option" 5.Input that material name in Fulltext search textbox and click "Enter" on keyboard. 6.Chec the search results whether right. 7.Modify those 50 material name as "material-1", "material-2"... "material-50". 8.In "Media" search, check those 50 material name whether display right. | 8. Those 50 material name display right: "material-1", "material-2"... "material-50". | 2 | ok
2-3 |  |  |  | Sync delete mateiral OA folder to NRCS | 1.Login Material Manage Terminal, D&D 50 material to OA folder of StudioA. 2.Login Octopus client . 3. Open "Media" on the right side of the menu from Octopus. 4.Click F4 on keyboard in input box(there is a prompt), then select StudioA on "select option" 5.Input that material name in Fulltext search textbox and click "Enter" on keyboard. 6.Chec the search results whether right. 7.In ML, deletre those 50 material. 8.In "Media" search, check those 50 material whether deleted. | 8.Those 50 material are deleted. | 2 | ok
2-4 |  |  |  | Sync new mateiral of ML to NRCS | 1.Login Material Manage Terminal, copy&paste 50 material in public node. 2.Login Octopus client . 3. Open "Media" on the right side of the menu from Octopus. 4.Click F4 on keyboard in input box(there is a prompt), then select ServerA on "select option" 5.Input that material name in Fulltext search textbox and click "Enter" on keyboard. 6.Chec the search results whether right. | 6.The search results is right. It display those 50 material. | 2 | ok
2-5 |  |  |  | Sync modify mateiral of ML to NRCS | 1.Login Material Manage Terminal, copy&paste 50 material in public node. 2.Login Octopus client . 3. Open "Media" on the right side of the menu from Octopus. 4.Click F4 on keyboard in input box(there is a prompt), then select ServerA on "select option" 5.Input that material name in Fulltext search textbox and click "Enter" on keyboard. 6.Chec the search results whether right. 7.Modify those 50 material name as "material-1", "material-2"... "material-50". 8.In "Media" search, check those 50 material name whether display right. | 8. Those 50 material name display right: "material-1", "material-2"... "material-50". | 2 | ok
2-6 |  |  |  | Sync delete mateiral of ML to NRCS | 1.Login Material Manage Terminal, copy&paste 50 material in public node. 2.Login Octopus client . 3. Open "Media" on the right side of the menu from Octopus. 4.Click F4 on keyboard in input box(there is a prompt), then select ServerA on "select option" 5.Input that material name in Fulltext search textbox and click "Enter" on keyboard. 6.Chec the search results whether right. 7.In ML, deletre those 50 material. 8.In "Media" search, check those 50 material whether deleted. | 8.Those 50 material are deleted. | 2 | ok
No.6
Issue ID |  | snp4100063909(EUSPSCTV-79)
Subsystem |  | GTM
Description |  | If there are more than two transfer server transfering, the GTM display the server name is always one transfer server.
Cause |  | It has not send transfer server name to GTM.
Why QA missed |  | Spec change
QA missed Test type |  | Function
Instant Action |  | Add to testing
Reproducible (yes/no) |  | Yes
Frequency |  | always
How to Fix |  | It send transfer server name to GTM.
Influence Range |  | No
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Display right transfer server name in GTM | Display right transfer server name in GTM | There are two transfer server transfering.
1-1 |  |  |  | 1.There are machine A(192.168.100.51) with 6000 and 6001 and machine B(192.168.100.73) with 6000 and 6001 | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2, event3 and event4 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material to all the event. 5.Check the transfer task is what transfer server transfering on Transfer Scheduler. 6.Login GTM, check the transfer server name whether right. | (only FYR) 5.On Transfer Scheduler,the 6000 of machineA transfering event1,and 6001 of machineA transfering event2. The 6000 of machineB transfering event3,and 6001 of machineB transfering event4. 6.On GTM, display that transfer server name is right: task event1 display server name as machineA name,and task event2 display server name as machineA name. task event3 display server name as machineB name,and task event4 display server name as machineB name. | 5 | ok
1-2 |  |  |  | 1.There is machine A(192.168.100.51) with 6000 and 6001 and machine | 1.Login NRCS client and create a rundown, story and event to StudioA that named rundown1,story1,event1, event2, event3 and event4 respectively, and create blank material to all the event. 2.Synch the rundown1 to Sonaps. 3.Login Material Manager Terminal. 4.Register material to all the event. 5.Check the transfer task is what transfer server transfering on Transfer Scheduler. 6.Login GTM, check the transfer server name whether right. | (only FYR) 5.On Transfer Scheduler,the 6000 transfering all of the transfer task 6.On GTM, display that transfer server name is right: all the task display server name as machineA name. | 5 | ok
No.7
Issue ID |  | snp4100064370
Subsystem |  | MOS
Description |  | Octopus send mosListAll message without the objPaths node.
Cause |  | The version number judgment, led to it not create objPaths node.
Why QA missed |  | This is an Octopus issue, but QA without Octopus.
QA missed Test type |  | Function
Instant Action |  | Add to testing
Reproducible (yes/no) |  | Yes
Frequency |  | always
How to Fix |  | Add objPaths node in mosListAll message.
Influence Range |  | NRCS send mosListAll message.
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | NRCS send mosListAll message. | Octopus send mosListAll message with objPaths. | NRCS=Octopus
1-1 |  |  |  |  | 1.Login Octopus client. 2.On the right side of the menu,click "Administration"->"MOS Devices"->"Devices" and then click "Content sync" on tool bar -> mosListAll sync->Request mosListAll from the MOS device. 3.Check the MOS message whether contain the objPaths under the ...\Sony\Sonaps\MosGateway\MOSMessageLog\ XML log. | 3.When sync finished, the MOS message contain the objPaths and right(Include sudio clip and ML material). | 5 | ok
1-2 |  |  | Octopus send mosListAll message whether right. | NRCS=Octopus | 1.Login Material Manager Terminal. 2.Copy&paste 30 material in the ML. 3.Register 30 material in the OA folder. 4.Login Octopus client. 5.On the right side of the menu,click "Administration"->"MOS Devices"->"Devices" and then click "Content sync" on tool bar -> mosListAll sync->Request mosListAll from the MOS device. 6.Check the MOS message whether contain the objPaths under the ...\Sony\Sonaps\MosGateway\MOSMessageLog\ XML log. | 2.Copy&paste successfully. 3.Register successfully. 6.When sync finished, the MOS message contain the objPaths and right(Include sudio clip and ML material), and mateiral sync to Octopus is right. | 5 | ok
No.8
Issue ID |  | snp4100064180(EUSPSCTV-158)
Subsystem |  | MOS
Description |  | PlaceHolder of the Octopus display is incorrect in OA Material folder of ML after modify title name of PlaceHolder in Octopus ML.(SP3 resolve) Octopus modify <objType>, <objGroup>, <objDur> and <description> values Sonaps responses NACK and update nothing.(SP4 resolve)
Cause |  | It is not give the ClipType value as null when update material. So cause the ClipType value always updated as default value 1 when each call for update interface.
Why QA missed |  | This is an Octopus issue, ENPS has no problem
QA missed Test type |  | Function
Instant Action |  | N/A
Reproducible (yes/no) |  | yes
Frequency |  | Always
How to Fix |  | It should be give the ClipType value as null when update material, avoid the ClipType value always updated as default value 1 when each call for update interface.
Influence Range |  | Modify material
Test Case | Test type | Function | Test viewpoint | Testcase condition | Operation | Expected result | Test times | Test Result
1 | Function | Update material | When modify placeholder title in Octopus, it can be display correctly. | NRCS=Octopus
1-1 |  |  |  | Modify title in Octopus | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open ML then found that placehoder of the event, and then modify its title name as "event=modified". 3.Login ML and check the placeholder of the event whether right in OA folder from ML. | 1.Create successfully. 2 and 3.In Octopus and OA folder, placeholder display right, the stamp no change, the title name as "event=modified". | 5 | ok
1-2 |  |  |  | Modify title in ML | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Login ML terminal then found that placeholder of the event, and then modify its title name as "event=modified-2". 3.Open ML and check the placeholder of the event whether right in Octopus. | 1.Create successfully. 2 and 3.In Octopus and OA folder, placeholder display right, the stamp no change, the title name as "event=modified-2". | 5 | ok
2 | function | modify material | When modify material title in Octopus, it can be display correctly. | NRCS=Octopus
2-1 |  |  |  | modify material in Octopus ML. | 1.Login Octopus client, and open ML window then select a material and modify its title name. And synch the rundown to Sonaps. 2. Login ML terminal then found that material, checkt it whether right. | 2. The material display right, and the stamp no change, and title right. | 5 | ok
2-2 |  |  |  | modify material in Octopus studio. | 1.Login Octopus client, and open ML window then select a material under the Studio and modify its title name. And synch the rundown to Sonaps. 2. Login ML terminal then found that material, checkt it whether right. | 2. The material display right, and the stamp no change, and title right. | 5 | ok
2-3 |  |  |  | modify material in ML terminal. | 1.Login ML terminal, and select a material and then modify its title name. 2.Login Octopus client then found that material, check it whether right. | 2. The material display right, and the stamp no change, and title right. | 5 | ok
2-4 |  |  |  | modify material in OA folder. | 1.Login ML terminal, and select a material under the Studio and then modify its name. 2.Login Octopus client then found that material, check it whether right. | 2. The material display right, and the stamp no change, and title right. | 5 | ok
3 | Function | Update material | Octopus modify <objType>, <objGroup>, <objDur> and <description> values Sonaps responses NACK and update nothing. | NRCS=Octopus
3-1 |  |  |  | Modify Type | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open ML then found that placehoder of the event, and then modify its Type value, and then save. 3.Login ML and check the placeholder of the event whether right in OA folder from ML. | 2.Save successfully, and Sonaps responses NACK and update nothing. 3.In OA folder, placeholder display right, the stamp and title name not change. | 5 | ok
3-2 |  |  |  | Modify Group | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open ML then found that placehoder of the event, and then modify its Group value, and then save. 3.Login ML and check the placeholder of the event whether right in OA folder from ML. | 2.Save successfully, and Sonaps responses NACK and update nothing. 3.In OA folder, placeholder display right, the stamp and title name not change. | 5 | ok
3-3 |  |  |  | Modify Duration | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open ML then found that placehoder of the event, and then modify its duration value, and then save. 3.Login ML and check the placeholder of the event whether right in OA folder from ML. | 2.Save successfully, and Sonaps responses NACK and update nothing. 3.In OA folder, placeholder display right, the stamp and title name not change. | 5 | ok
3-4 |  |  |  | Modify Description | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open Media then found that placehoder of the event, and then modify its description value, and then save. 3.Login ML and check the placeholder of the event whether right in OA folder from ML. | 2.Save successfully, and Sonaps responses NACK and update nothing. 3.In OA folder, placeholder display right, the stamp and title name not change. | 5 | ok
4 | Function | Update material | When modify placeholder title, Type, Group, Duration, and description in Octopus, it can be display correctly. | NRCS=Octopus
4-1 |  |  |  | modify placeholder title, Type, Group, Duration, and description | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open Media then found that placehoder of the event, and then modify its title, Type, Group, Duration, and description value, and then save. | 2.Save successfully, and only midify title name successfully, other is NACK and update nothing. | 5 | ok
4-2 |  |  |  | Not any modify. | 1.Login Octopus client and then create a rundown, story and event and event create blank material. And synch the rundown to Sonaps. 2.Open Media then found that placehoder of the event, and eidt it but not any modify, and then save. | 2.Save successfully. Not any modify of this placehoder in Octopus and ML. | 5 | ok
Note on A2: 作者: CQ ID and CHLOE ID
Note on A10: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B13: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A28: 作者: CQ ID and CHLOE ID
Note on A36: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B39: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A89: 作者: CQ ID and CHLOE ID
Note on A97: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B100: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A106: 作者: CQ ID and CHLOE ID
Note on A114: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B117: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A123: 作者: CQ ID and CHLOE ID
Note on A131: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B134: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A147: 作者: CQ ID and CHLOE ID
Note on A155: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B158: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A164: 作者: CQ ID and CHLOE ID
Note on A172: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B175: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test
Note on A180: 作者: CQ ID and CHLOE ID
Note on A188: 作者: Frequency of on-site: always/offten/sometimes/one time
Note on B191: Please consider the following item if needed: Function State Transition Compatibility Accuracy Boundary Value Fail Safe/Fool Proof Competition Parallel Operation/Background Operation Long Term Stability Backup/Restore Change Setup Install/Uninstall/Update/Setting System Maintenance/Service Performance Single Stress Over Load Acceleration Volume Machine Trouble System Machine Trouble Network Trouble Machine Configuration Network Configuration OS/Browser Version Mixture Network Security Idea Test

## Release note check
序号 | Category | Description | Result | 加权分值
1 | Spelling Mistake or grammar mistake | Words spelling mistake - Use the default spell check tool of Words to find this mistake. Words missing, Expression imcomplete. - Due to the leters limitation in CQ headline, some sentences miss some words. Expression mistake(e.g. Grammar mistake) - The limitation part in RN must be easy for user to understand. Words capital/small mistake - e.g.mxf, SONAPS, Safs etc. Space between words missing, punctuation mistake. - Space between words missing, which result in inconvenient reading. - Chinses punctuation. | OK | #REF!
2 | Softaware/driver version | 。 | OK
3 | Format mistake | The font shoulb the clear, no error code The font size should be proper The font should be the same as other documents: - 5.4 SAFS Configuration Manual is not the same as others, No chapter sign but · Long-chapter description should be divided into smaller chapters: Line space and indentation mistake: - Sometimes in document reference, the chapter name is wrong - The indentation of sub-chapter is too large All the final documents, including PDF and Chm, should be copied and searched normally: - When Word transcode to PDF, it can't be copied and searched normally, suggest to use Acrobat for transcoding - In japanese OS, the Installation Manual.chm can not be searched | OK
4 | Screenshots | The screenshot mistake: - No screenshots to key procedure, - The lacation of the screenshots are incorrect - The screenshot is not the same as the real system - Some setting screenshots are not showing the correct information - The screenshot is using the wrong patch - The screenshot is not clear with no word description - The screenshot is in chinese language - Some screenshot are taken by cellphone, e.g. BIOS [Sony QA]The screenshot cannot contain the 3rd party logo or other information involved with copyright - In User's Guide, there are lots of the screenshot with water mark "MTV""BBC"etc - In LiveLogging document, Some screenshots contain the logo of Bayern Some part of the document is with screenshot and with out describetion: The screenshots should be with the name and number | OK
5 | Setting description mistake | The setting should be with clear description: - e.g. In Web Sonaps Configuration Manual, user should set "SmiDirectory " but there is no related description. The description is not the same as the real system: - e.g. In AIS Installation, SonapsDB setting of Memory is recommand to be 400M, But it should be 40% of the memory, - e.g. the system can do 4-channel ingest at the same time, but in document it says:ServerCount: How many import tasks can be supported at same time. It’s should be 1. - In 532P3 Installation manually, it says the Start Time Code is : 1: VITC / 2:LTC / 3:FTC, But the correct one should be : 0:VITC;1:FTC;2:LTC When refer to do some settings changing in net manager, there is no detail information: - No default value - No example - No suggestion about reference documents | OK
6 | Operation procedure | Settings in a sonaps application, it should be with: - The exact file location - Should describe from which button or which menu The procedure should be correct: The procedure should be with the description to make the purpose clear The operation in which machine should be clear: - e.g. in installtion document chapter 1 "8. Set UAC to the lowest level for before Sonaps system installation", The terminal or server should be clear The Note should be clear, especially for special status: - e.g.in 532P3 document, in Background Server chapter, after Run.bat, the Serveice Management Framework will show Not Start status. But it's normal and should be pointed out The place of Note and Warning should be correct: - In 5.4 SAFS Configuration Manual, Waring is always shown at the end | OK
7 | 5.4 New feature | The document should include the 5.4 new feature: The description of the new feature should be clear: If the feature in 5.4 is not supported anymore, should be pointed out In RN, the Major Fixed Issues and the Known Issues part should be with the bug id | OK
8 | Document reference | When refer other documents, should use the correct name(the format and the patch information: - e.g. "please refer Sonaps_v5.4_xxxx.docx" , "Sonaps V5.4P3_xxx.xlsx" - e.g. "please refer Sonaps_5.3.2P3_SAMS_Configuration…" When refer to other chapter in other documents, should provide the link or correct location: - If the document is in the eCsite, there is no need to describe When refer to other chapter in other documents, the wrong chapter is provided: - e.g. in SAFS Configuration manual "Refer to Note 3" , Note3's lacation is not clear etc. The reference link is wrong(dead link) - e.g. in Installation Manul there is a Web site button will refer to 3rd party website - e.g. in Open Interface, there are a lot of wrong link The reference document must be released offically | OK
9 | Proper noun | The proprt noun and the computer's name should be the same (Refer to "Sonaps_V5.4_APL_Module_Arrangement.xls"): - Name misusage, e.g. SAMS is corrcect, but in some other place it's MSV - e.g. in the installation document, the computer name is sometimes "MSV", and sometimes "Ingest Device for SD/HD", - e.g. in MOSProtocolSupport, there are several name for Newsroom computing system: NRCS，NCS，NRC etc. When the abberviation show for the first time, there should be the full description: - e.g. in installtion document, IMS was mentioned for the first time, but there is no full name (Ingest Management Server) - In RN, there is some other abberviation: EM、LM、LLM、PL etc, it shoulb be with full name. - 3rd party soft/hardware FCP => Final Cut Pro The measurement unit should be the same: - e.g. MB, GB, bps, sec , etc | OK
10 | Special noun | [Sony QA]The document should be in English [Sony QA]Draf, personal name, watermark shouldn't be in document [Sony QA]No confidential words, e.g. "CONFIDENTIAL" ,“SECRET”,"INTERNAL USE ONLY"; [Sony QA]No "Mute" , "Slave", "Male", "Female", "B/W" [Sony QA]No BZNS-700, BZNS-2000 description | OK
| Copyright Related | When describing 3rd party product, it should add the company name for the first time. - 3rd party soft/hardware, e.g. Final Cut Pro (Apple Inc.) All the document and the screenshots cannot contain 3rd party Logo or other information related to copyright - no pictures involved with portraiture right - no screenshots to films, series The documents should contain the describition to necessary copyright - The description should be correct (Refer to Sony Guideline) - The year information should be correct - e.g.©2014 Sony Corporation. All rights reserved. - The patch information and release date | OK
| Personal information | There should be no personla information in the document - e.g. personal name, email address There should be no unnecessary internal information - no classified information. e.g. "CONFIDENTIAL" ,“SECRET”,"INTERNAL USE ONLY"; The properties of Office Document(Excel, Word) and PDT Document should not contain any personal or company information - e.g. The writter is PDT X - e.g. company name: Sobey PDT | OK
| Consistency | The contents of the Document (especial for installation, and cofiguration) should be same as the real system - e.g. The installation document, contents and precedure should be same as the real system When patch released, the contents in Release Note and Test Report should be the same - e.g.The issues, cause and how to fix in release note should be the same as the coresponding test report | OK
| Special Sign | When use ellipsis, should be like … When use multiplication sign, should be like * - Don't use x | OK
| Date | The display of the date, should be as mouth day, year ,Should not be all in number(Under special cituation will result in misunderstood) - OK ■February 23, 2000 ■June 11, 1999 - NG ■23 February 2000 ■6/11/99 ■11/6/99 ■April 21st The update date should be the same as real The release date should be the same as real | OK
| Chapter number and catalog | The catalogs should be same as the main text in the document - No dead link or unsynchronization. The Chapter number should be correct - No duplicate chapter number or the chapter is not continous | OK
| Document Statement | For certain document(especially for installation and configuration), if the knowledge of the user is required, the document should point it out. | OK
| Released file format | The text choosing fuction in PDF format should be normal - e.g. Choose some part of the text, copy it and paste on the notepad, the text is correct The searching funtion is PDF, CHM format should be normal Under other OS, the display should be normal - e.g. under japanese OS, the documents is in error code - e.g. under japanese OS, the search function in CHM cannot be used PDF, Word, CHM, EXCEL format document can be open normally under different software version - If under special cituation, e.g. some special tool, it should be mentioned in the document - e.g. the document made in Word2010, should be opened in Word2007, 2003 | OK
19 | Final document format/name | [Sony QA]The conpressed file should be in Zip format - QA should use the windows zip function to unzip that version files/patch/DB script/drivers; [Sony QA]Final format:execl as mhtl,word as PDF; [Sony QA]The file suffix cannot be *.bat, *.exe [Sony QA]Name of documents cannot contain space and non-ascii charater(【】..), the size should be less than 2GB [Sony QA]The edit, review and comment information should not be contained in the final version [Sony QA]The documents on Ftp208 should be latest version [Sony QA]No chinese documents should be in ftp 208 [Sony QA]The final version (documents and program) should be the same as those QAed. the Hash value should be the same | OK
| Special documents | For some documents cannot be Qaed, PDT should check it carefully and feedback the corrected result - e.g. in "License Application", "Paper" License is correct or not | OK

## release file check
Result
General
| Confirmtion the result of binary check between on FTP and QA'ed by PDT. | OK
| Get the MD5 hash values of each files on FTP from PDT and copy to below. | OK
ede4ab530ccb1fb6b2f1e0f0ec2abe79 \McAfee.JPG
1a29e8417a59db2b20c758234a5c0ae3 \Sonaps V5.4.2 SP4.zip
a46e7c32b22916507a9945e18d5bb7d4 \Sonaps_V5.4.2_SP4_Release_Notes.pdf
91c5082a4406e7dc2dbb072abb5a7c7f \V5.4.2 SP4.ais
| The final file on FTP and QA'ed are the same.(by binary check) | OK
| RAR format is not used. | OK
| Chinese is not incuded in the release document. | OK
Release notes
| The patch version and the base version are clear. | OK
| The release target is clear. | OK
| The fixed bug information and test case are the same. | OK
| The upgrade/rollback procedure (especially which PC should be stopped) are the correct. | OK
| The patch file list and path are the correct. | OK
| Release note includes CQ & CHLOE id | OK
| ATG QA checked and feed back OK | OK
Anti-virus check
| The screen shot is provided from PDT. | OK
| It was checked by the latest anti-virus DB. | OK
MD5 hash | (please check the MD5 hash of each files and copy to below)
| The MD5 hash are same between PDT's & QA's | OK
ede4ab530ccb1fb6b2f1e0f0ec2abe79 1027\McAfee.JPG
1a29e8417a59db2b20c758234a5c0ae3 1027\Sonaps V5.4.2 SP4.zip
a46e7c32b22916507a9945e18d5bb7d4 1027\Sonaps_V5.4.2_SP4_Release_Notes.pdf
91c5082a4406e7dc2dbb072abb5a7c7f 1027\V5.4.2 SP4.ais

## download check
Result
Double check the IBG result
Every items are filled in [release file ckeck] sheet
Virus is checked by the latest anti-virus DB (difference on several days is acceptable)
Download check
The release file is uploaded to below URL:
ftp://
Every files can be downloaded from above FTP
MD5 hash of FTP and IBG result are the same, and copy the hash to below.
The file which doesn't need a release is deleated (such as anti-virus result, thumbs.db)
The zip file can be un-zipped

## history
Revision | Date | description
Liuxiang | 2012-01-11 | Improve file check item
Wasaki | 2013-09-24 | Improve test report format as follows.
(1)The following items are added. ・Subsystem: Write the subsystem which written in "pre-test report" sheet. Because it is easy to understand XPRI or Sonaps ・QA missed Test type: Write what kind of test type QA missed. It will improve test design skilｌ of QA team. ・Reproducible (yes/no): Write the problem is reproducible or not. ・Frequency (always/offten/sometimes/one time): Write the frequency which the problem happen.
(2) Based on Kageyama-san's request, the most left blank column was deleted. Also 1st and 2nd blank line of top were deleted.
(3)The column width of Test type was too wide. The column width of Testcase condition, Operation and Expected result were too narrow. So it was inconvenient to review. These issues were improved as follows. - The columns from "Patch for" to "Release Date" in test report header were shifted to left side. - The title field in header consists of not 1 column but 2 columns. The columns of Testcase and Test type were shortened. - Also the individual column width of Function, Test viewpoint, Testcase condition, Operation and Expected result was adjusted. - The position of Test times, Test Result, Severity and Current status in trailer are moved to right side.
(4) Based on Kageyama-san's request, the outline of Operation and Expected result column is grouped. It makes easier for managers to review the test result at release judgment meeting. They can be hidden or shown as needed. Please uncheck the check box of "Summary rows below detail" and "Summary columns to right of detail" as shown below.
(5) There were so many unnecessary blank columns in right side of Test Result column. When a horizontal scroll bar is moved even a little, it moves to an unnecessary column. So those unncessary blan columns are deleted.
TestType sheet is added. It describes individual test type.